- IPC REFORM WORK PROGRAM

- (IPC/REF/7 FOLLOW-UP ACTIONS)

| Task (project file) | IPC/REF/7/3 paragraphs | Action | by | Date |
| --- | --- | --- | --- | --- |
| 4 (IPC/R 4/99) | 31 | Complete survey of notes specifying multi-aspect classification | IB | 15.06.02 |
|  |  | Comments on the survey | IPC/REF members | 15.09.02 |
|  |  | Rapporteur report | IB | 15.10.02 |
| 8 (IPC/R 8/99) | 37-42 | Verification of the new presentation of IPC symbols | IPC/REF members | 01.11.02 |
| 10 (IPC/R 10/99) | 55 | Suggestions for supplementing the IPC FAQ | IPC/REF members | 01.09.02 |
| 14 (IPC/R 14/00) | 57-61 | Distribution of groups in last and first place rule areas, except classes C07 and C08 | IB | 01.10.02 |
|  |  | Proposal for distribution of groups in classes C07 and C08 | EP | 01.10.02 |
| 15 (IPC/R 15/00 | 62-64 | Comments on Guidelines where to classify | IPC/REF members | 15.09.02 |
|  |  | Rapporteur report | US | 15.10.02 |
|  | 26-29 | Comments on the proposal for resudal subclasses and main groups | IPC/REF members | 15.09.02 |
|  |  | Rapporteur report | US | 15.10.02 |
| 16 (IPC/R 16/00) | 17-20 | Background material for discussion | IB | 15.09.02 |
| 17 (IPC/R 17/01) | 67-68 | Comments on the remaining terms in the Glossary | IPC/REF members | 01.09.02 |
|  |  | Rapporteur report | US | 01.10.02 |
|  | 71-75 | New chapter in the Guide on the use of the IPC for searching | IB | 15.08.02 |
|  |  | Comments on the Guide | IPC/REF members | 15.09.02 |
| 19 (IPC/R 19/02) | 21-25 | Detailed IPC maintenance procedure | SE | 15.08.02 |
|  |  | Comments on the procedure | IPC/REF members | 15.09.02 |
|  |  | Rapporteur report | SE | 15.10.02 |