IPC DEVELOPMENT PROGRAM

| Task No. | Task Title | Action | Timeline |
| --- | --- | --- | --- |
| Continuous tasks |
| 1 | Elaboration of classification definitions |  |  |
| 1(a) | Develop a plan for completion of all subclass definitions | Prepare an updated list of priorities Prepare a list of prioritized subclasses | Q2/2006 Q4/2006 |
| 1(b) | Preparation of definitions | Complete definitions for an additional 50 subclasses | Q4/2008 |
| 2 | Systematic maintenance of the IPC |  |  |
| 2(a) | Develop a plan for maintenance of all subclasses | Prepare an updated list of priorities Start pilot projects | Q2/2006 |
| 2(b) | Treatment of maintenance projects | Complete maintenance of 10 subclasses | Q4/2007 |
| 3 | Removal of informative references in IPC schemes | Remove informative references from the IPC schemes after completion of corresponding D-projects | As needed |
| 4 | Removal of references from guidance headings |  |  |
| 4(a) | Develop a plan for removal of references from guidance headings in all subclasses | Develop plan | Q2/2006 |
| 4(b) | Removal of references | Remove all references from guidance headings and relocate them in appropriate groups (i.e., limiting type) or in the electronic layer (i.e., informative type) | Q4/2007 |
| 5 | Special Residual Subclasses and Residual Main Groups |  |  |
| 5(a) | Introduction of residual main groups in IPC schemes | Create residual main groups where appropriate | Q1/2008 |
| 5(b) | Maintenance of special residual subclasses and main groups in IPC schemes | Develop a procedure Periodical review of all residual subclasses and main groups for emerging technologies or classification problems | Q2/2006 Continuous |
| Ad hoc tasks |
| 6 | Treating revision projects | Treat CL projects and projects which are forwarded from the ALS | As needed |
| 7 | Update of IPC training examples | Update existing training examples following a revision project. Introduce a new training example when a new subclass is introduced or an existing one is extensively revised | As needed |
| 8 | Correction of obvious errors or deficiencies in IPC schemes or definitions | The IB will evaluate proposals for correcting obvious errors in IPC schemes or definitions and refer to ALS or WG, if appropriate. IB will correct evident clerical errors without further action. | As needed |
| 9 | Evaluate borderlines between core and advanced level in schemes for problems with hierarchy, ease of use, and correctness of notes, examples or references | Evaluate and propose improvements to the schemes, notes, examples or references and refer task to ALS when appropriate | As needed |
| 10 | IPC Guide or Handbook improvement | Evaluate proposals for new or revised principles or rules for the IPC and propose corresponding changes to the Guide. Update the Handbook to reflect any changes in the Guide and Guidelines | Q4/2007 |
| 11 | Quality control of IPC classification | Develop a procedure for investigating significant discrepancies reported between classification symbols applied to members of simple patent families. Propose corrective actions as appropriate | Q2/2007 Continuous |
| 12 | Preparation of new IPC edition |  | Q1/2008 |

[Technical Annexes follow]