# RECENT ACTIVITIES AND WORK PLAN FOR UPDATING SURVEYS PUBLISHED IN PART 7 OF THE WIPO HANDBOOK

This document contains the proposal on the tentative work plan for the Task on the continuous maintenance and update of Part 7 of the WIPO Handbook (Task No. 50).  Actions proposed for each survey are indicated in Annex I to the present document.

## PROPOSED ACTIONS LISTED BY SURVEY

### Part 7.1 “Representation of calendar dates”

- (CWS/7, 2019) request Part 7 Task Force to prepare a questionnaire on the presentation of dates;

- (CWS/8, 2020) approve the questionnaire, request the survey update;  and

- (CWS/9, 2021) note survey results and approve publication of the updated survey in the WIPO Handbook.

### Part 7.2.1 “Presentation of application numbers”

- (CWS/5, 2017) agree to move Part 7.2.1 to the Archive following the transfer of information to Parts 7.2.6 and Parts 7.2.7.

### Part 7.2.2 “Survey of numbering systems used, or intended to be used, by industrial property offices with regard to applications, published documents and registered rights”

- (CWS/6, 2017) request Part 7 Task Force to prepare a questionnaire on publication and registration numbers;

- (CWS/7, 2018) approve the questionnaire, request that the survey be conducted;  and

- (CWS/8, 2019) note the survey results, approve publication of the new survey in the WIPO Handbook, and agree to move section 1 of Part 7.2.2 on application numbering to the Archive.

### Part 7.2.3 “Numbering systems and date formats introduced or planned to be applied with regard to the arrival of the year 2000”

- (CWS/8, 2020) agree to move Part 7.2.3 to the Archive following the update of Part 7.1.

### Part 7.2.4 “Survey on the presentation of priority application numbers”

- To be updated regularly;

- (CWS/5, 2017) announce the update of the survey to be carried out during the following year;  and

- (CWS/6, 2018) note the amendments, if any.

### Part 7.2.5 “Survey on application numbering systems”

- No updates required so far.  Eventual updates to be requested by the CWS.

### Part 7.2.6 “Numbering of applications and priority applications – Current practices”

### Part 7.2.7 “Numbering of applications and priority applications – Former practices”

- To be updated regularly;

- (CWS/5, 2017) note the survey results (Part 7.2.7), note the amendments (Part 7.2.6);

- (CWS/8, 2020) announce the update of the surveys to be carried out during the following year;  and

- (CWS/9, 2021) note the amendments, if any.

### Part 7.3 “Examples and kinds of patent documents”

- To be updated regularly;

- (CWS/7, 2019) announce the update of the survey to be carried out during the following year;  and

- (CWS/8, 2020) note the amendments, if any.

### Part 7.4 “Correction procedures”

- No updates required so far.  Eventual updates to be requested by the CWS.

### Part 7.5 “Physical characteristics of patent documents”

- In the Archive.

### Part 7.6 “Survey of bibliographic information contained in patent gazettes …”

- (CWS/8, 2020) request Part 7 Task Force to review the questionnaire;

- (CWS/9, 2021) approve the questionnaire, request that the survey be conducted;

- (CWS/10, 2022) note the survey results and approve the publication in the WIPO Handbook.

### Part 7.7 “Survey on the grant and publication of “Supplementary Protection Certificates” …”

- (CWS/6, 2017) approve the questionnaire, request that the survey be updated;

- (CWS/7, 2018) note the survey results, approve publication of the updated survey in the WIPO Handbook;  and

- (CWS/9, 2012) announce the update of the survey to be carried out during the following year.

### Part 7.8 “Survey of filing procedures and filing requirements, as well as of examination methods and publication procedures, relating to industrial designs”

- in the Archive.

### Part 7.9 “Survey concerning citation practices in industrial property offices”

- No updates required so far.  Eventual updates to be requested by the CWS.

### Part 7.10 “Survey of practices in industrial property offices regarding codes used for internal purposes or individual use”

- No updates required so far.  Eventual updates to be requested by the CWS.

### Part 7.11 “Survey on the implementation and promotion of WIPO Standard ST.22”

- No updates required so far.  Eventual updates to be requested by the CWS.

### Part 7.12 “Survey on the use of WIPO Standards”

- (CWS/5, 2017) note the survey results, approve publication of the new survey in the WIPO Handbook (see document CWS/5/2)

## TENTATIVE SCHEDULE OF PROPOSED ACTIONS

The table below contains visual and less detailed representation of the information provided in the list above:

|  | Last publ. | After CWS/5 2017 | after CWS/6 2018 | after CWS/7 2019 | after CWS/8 2020 | after CWS/9 2021 |
| --- | --- | --- | --- | --- | --- | --- |
| Part 7.1 | 1997 |  |  | Questionnaire | Collect Info | Publish |
| Part 7.2.1 |  | Archived |  |  |  |  |
| Part 7.2.2 | 2001 |  | Questionnaire | Collect Info | Publish |  |
| Part 7.2.3 | 2000 |  |  |  | Archiving |  |
| Part 7.2.4 | 2018 |  | Update / Publish |  |  | Update |
| Part 7.2.5 | 2013 | Update on request from CWS |  |  |  |  |
| Part 7.2.6 | 2017 |  |  |  | Collect Info / Publish |  |
| Part 7.2.7 | 2017 | Publish |  |  | Collect Info / Publish |  |
| Part 7.3 | 2016 |  |  | Collect Info / Publish |  |  |
| Part 7.4 | 2009 | Update on request from CWS |  |  |  |  |
| Part 7.5 |  | Archived |  |  |  |  |
| Part 7.6 | 1990 |  |  | Questionnaire | Update | Publish |
| Part 7.7 | 2002 | Questionnaire | Update | Publish |  | Update |
| Part 7.8 |  | Archived |  |  |  |  |
| Part 7.9 | 2008 | Update on request from CWS |  |  |  |  |
| Part 7.10 | 2009 | Update on request from CWS |  |  |  |  |
| Part 7.11 | 2012 | Update on request from CWS |  |  |  |  |
| Part 7.12 | 2018 | Publication | Ad-hoc updates on request |  |  |  |

## ACTIONS FOR THE YEAR 2018/2019 (FROM CWS/7 TO CWS/8)

- Part 7 Task Force

  - Draft survey for 7.1 representation of calendar dates;  and

  - Draft survey for 7.6 bibliographic information in patent gazettes.

- Part 7.2.2 numbering systems for publications and registrations

  - Invite IPOs to respond to survey and collect responses;  and

  - Prepare report on results for CWS/8.

- Part 7.7 grant and publication of industrial property protection extensions (IPPEs)

  - Publish results.

- Part 7.3 examples and kinds of patent documents

  - Invite IPOs to update their entries in the Handbook.

[Конец Приложения и документа]

[Endnote continued from previous page]

[Endnote continued on next page]

[Footnote continued from previous page]

[Footnote continued on next page]