E

MM/A/43/1

OriGINAL:  English

DATE:  July 20, 2010

Special Union for the International Registration of Marks 
(Madrid Union)

Assembly

Forty-Third (25th Extraordinary) Session

Geneva, September 20 to 29, 2010

INFORMATION TECHNOLOGY MODERNIZATION PROGRAM (MADRID AND HAGUE INTERNATIONAL REGISTRATION SYSTEMS):

PROGRESS REPORT

prepared by the International Bureau

INTRODUCTION

- A comprehensive document describing the approach to and the resourcing of, the IT Modernization Program was presented to the forty-second session of the Assembly of the Madrid Union in September 2009.  The document MM/A/42/2 is reproduced for convenience in the Annex to this document, and shall serve as the baseline from which subsequent IT Modernization Program progress is subsequently reported to the Assembly of the Madrid Union.

- The purpose of the present document is to outline such progress on the IT Modernization Program since the last Madrid Union Assembly.  This document shall also update member States on any change to the overall approach to the completion of the Program, as well as notify changes to the Program schedule.

- It is recalled that the IT Modernization Program was originally to be conducted in three phases, with the third Phase being optional and only to be initiated where there was a clear business requirement to do so.  Phase I consisted of sub-projects that would produce immediate positive results, together with other sub-projects that would lay the technical foundations for subsequent program phases.  The second Phase would build

upon the achievements of Phase I without necessarily changing the database architecture of the legacy systems, whilst Phase III foresaw the introduction of a new database technical architecture which would necessitate the full redevelopment of the legacy systems.

- It is further recalled that at its forty-second session, the Madrid Union Assembly approved a revised approach to and the resource envelope to achieve, the subsequent program phases.  The revised approach combined Phases II and III into a single initiative (hereinafter known as Phase II) and the resource envelop amounted to 8.731 million Swiss francs from the Madrid Union, and 3 million Swiss francs from the Hague Union.

It should also be noted that the scheduled completion of the new Phase II was originally planned for the third quarter of 2012 (see paragraph 30 of the Annex), rather than by the end of 2011, as indicated in the report of the forty-second session of the Madrid Union Assembly.

PHASE I – IMPLEMENTATION STATUS

- A key milestone in Phase I was the migration of the legacy systems from a mainframe platform to a more cost effective UNIX platform.  This achievement took place in February 2010 and was a key element towards the goal of operational cost reduction, and the establishment of an appropriate technical platform upon which subsequent technology sub-projects could be based.

- The Service Oriented Architecture (SOA) Proof of Concept was successfully concluded in April 2010, after initially encountering a number of delays associated with internal administrative procedures.  This exercise confirmed that the technologies that had been chosen for the creation of web services performed according to specification and therefore fully met business requirements.  The Proof of Concept exercise involved the creation of a bona fide Madrid transaction using the SOA technology, and was successful to the extent that the resultant transaction would be migrated to the production environment as part of the SOA Pilot exercise.

- The SOA Office Pilot was initiated in July 2010 with the establishment of a Terms of Reference document after consultation with three participating Offices (BX, CH and PT).  The Office Pilot will ensure that the SOA environment is externally accessible by the technical infrastructure of the participating Offices.  The Terms of Reference negotiated with the offices for the Office Pilot are more ambitious than originally intended due to the level of success of, and the confidence gained from, the preceding Proof of Concept exercise.  The SOA Office Pilot exercise is scheduled for completion at the end of 2010, and if it is successful, we will have laid a very solid foundation for Phase II of the IT Modernization Program.

- The use of Phase I tools for the purposes of re-engineering some internal processes has also been initiated.  The Madrid System Goods and Services Database has been exploited by internal processes for the purposes of pre-translating expressions of goods and services included in international applications.  The aim of this exercise is, to the extent possible, to only translate goods and services that have not been translated before.  The revised translation procedure is currently used on a daily basis and is yielding a 50% efficiency gain in translation (i.e. we are translating 50% less), and will become even more efficient when the internal Goods and Services Database is supplemented with the most frequent goods and services terms inscribed in the International Register since 2008.

- A similar approach is intended to be followed in the re-engineering of the goods and services classification processes where the eventual aim is to present to our classification examiners only goods and services terms that have hitherto not been classified by the International Bureau.  It is expected that efficiency gains in this area will be equivalent to those being attained in the pre-translation exercise mentioned above, and that a re engineered procedure for classification will be in place prior to the 2010 Madrid Union Assembly.

- Re-engineering of the refusal examination process has also taken place.  This exercise has been restricted to the pre-selection of refusals communicated to the International Bureau in electronic form with the aim of conducting a fully automatic examination.  It is expected that more than 50% of refusals received electronically can be examined electronically.  It is further expected that the re-engineered procedure be in place prior to the Madrid Union Assembly.

- The Madrid Portfolio Manager and the Madrid Electronic Alert services have been made available for testing by external users, and thus far have been proven to be fit for service.  Since such services will provide online communication to Madrid system clients and third parties, it is essential that appropriate International Bureau back-office processes assuring persistent client assistance are in place prior to making the services generally available.  It is expected that these processes will be assured and that the Madrid Portfolio Manager and the Madrid Electronic Alert will be available, before the end of 2010.

- The sub-projects making up Phase I of the IT Modernization Program have yielded numerous positive results, many of which are available to internal and external users of the International Bureau’s systems.  The conclusion of the SOA Office Pilot at the end of 2010 will see the end of all activity under Phase I, which was originally planned to be completed by the end of 2008-2009, and all of which has been undertaken within the original Phase I resource envelope of 5.028 million Swiss francs.

PHASE II – IMPLEMENTATION STATUS

- It is recalled that the approved approach to the execution of Phase II is to identify an external strategic partner, following an open international tender, with a view to selecting a suitably qualified and experienced company that would:

  - undertake a technical assessment of the legacy systems and databases, including the SOA technologies, for the purposes of converting them into a new technical architecture;

  - propose an appropriate target technical architecture, also taking into account the results of the SOA Proof of Concept and Office Pilot exercises; and

  - prepare a fixed price offer for the conversion of the legacy software and data structures to the proposed new technical architecture, including preparation of the necessary web services using the SOA technologies, the execution of subsequent system testing and the establishment of systems performance benchmarks, together with an appropriate warranty period.

- It should also be recalled that the longer term operational support of the resultant technical environment would be modeled upon the successful approach currently in place for WIPO’s ERP systems – i.e., contracts would be concluded with an external partner for the ongoing maintenance and development of the solution.  Such contracts would be

administered by a core internal team of technical experts with strong business knowledge.  The internal team would be responsible for the day-to-day operation of the system and minor enhancements.

- The initiation of Phase II was strictly dependant on the conclusions of the SOA Proof of Concept exercise.  After a number of delays as mentioned above, the SOA Proof of Concept was concluded in April 2010 and it is now clear that the SOA technologies will necessarily become a fundamental element of the future technical architecture, subject to the successful conclusion of the SOA Office Pilot.

- Given the delays in the SOA sub-project, it is now proposed to initiate Phase II of the Modernization Program in the third quarter of 2010, according to the draft schedule appearing below:

- From the above timelines, it is clear that the focus of Phase II activity for the remainder of 2010 shall be upon the identification of the strategic partner, which is scheduled to commence work in early 2011 and complete the project by the end of 2012.

- It should be noted that for the moment it is impossible to present a more granular project execution time line.  Such a granular time line will be the first deliverable, once the project execution task is initiated in January 2011, with the selected company.

- Due to the delayed initiation of Phase II, the resource envelope approved by the forty-second session of the Assembly of the Madrid Union (8.731 million Swiss francs) and the twenty-eighth session of the Hague Assembly (3 million Swiss francs) has not been utilized, therefore the resources remaining available for Phase II of the IT Modernization Program amounts to 11.731 million Swiss francs.

20.	The Assembly is invited to

(i)	take note of the status of implementation of Phase I of the IT Modernization Program;

(ii)	take note of the revised schedule for the implementation of Phase II of the IT Modernization Program, with an expected completion date of December 2012.

[Annex follows]

| WIPO |  | E MM/A/42/2 ORIGINAL: English DATE: August 15, 2009 |
| --- | --- | --- |
| WORLD INTELLECTUAL PROPERTY ORGANIZATION |
| GENEVA |

SPECIAL UNION FOR THE INTERNATIONAL REGISTRATION OF MARKS
(MADRID UNION)

ASSEMBLY

Forty-Second (18th Ordinary) Session

Geneva, September 22 to October 1, 2009

INFORMATION TECHNOLOGY MODERNIZATION Program
(Madrid and Hague international registration systems): 
status report and proposed next steps

prepared by the International Bureau

I.	INTRODUCTION

1.	The purpose of the present document is two-fold.  It contains a report prepared by the International Bureau on the implementation status of the Information Technology (IT) Modernization Program of the Madrid and Hague IT support systems, as described in documents MM/A/38/4 and H/A/24/2 and summarized in Annex I below.  It also lays out how implementation of the Program could be pursued further.

2.	Initiation of this IT Modernization Program was approved by the Assemblies of the Madrid Union and the Hague Union in September 2007.  The Program was scheduled to be implemented in two phases over a period of four years (2008-2011), with the possible addition of a third phase, for a total estimated cost of some 15.3 million Swiss francs for the three phases.  A first status report was presented to the Assemblies of the Madrid Union and the Hague Union in September 2008 and is contained in documents MM/A/40/3 and H/A/26/2.

3.	Implementation of Phase I of the program was approved by the Assemblies against an estimated investment cost of 5.028 million Swiss francs, to be financed as follows:

–	2.9 million Swiss francs from programs 18 (1 million) and 27 (1.9 million) under the initial Program and Budget for 2008/09 – i.e., programs 6 and 25 under the Revised Program and Budget for that biennium;

–	2.128 million Swiss francs from the surplus generated by the Madrid Union budget by the end of 2007.

4.	The Madrid Union Assembly further approved that any amount of the above-mentioned surplus exceeding the amount necessary to reach the target level of reserves (25 per cent of the estimated biennial expenditure in the 2008/09 biennium (PBE factor)) be kept within the Madrid Union Reserve and Working Capital Funds with a view to contributing to the financing of subsequent stages of the IT Modernization Program.

- PHASE I – IMPLEMENTATION STATUS

5.	Within the first 18 months of implementation of Phase I (from January 2008 to June 2009), considerable progress has been made concerning several sub-projects, notably Sub-Projects A1, A2, A5, A6, A7, B1 and B5.

(a)	Enhancing internal productivity

6.	This goal will be achieved with the completion of Sub-Projects A1 to A7.  Sub-Projects A1, A2, A5, A6 and A7 will be completed in the course of 2009.

7.	Under Sub-Project A1 (Translation), an application aiming at automating the translation of limitations, subsequent designations and final decisions concerning trademark registrations by recycling those parts of the lists of goods and services already contained in the original registration, is being tested.  It is planned to be in production as from September 2009.

8.	Under Sub-Project A2 (Classification), a web application aimed at assisting users of the Madrid system in composing lists of goods and services containing correctly classified indications is being developed.  This e-classification tool will allow users to make searches in a database of acceptable indications of goods and services, validated by the International Bureau.  As of May 2009, a prototype of this application is being tested.

9.	Under Sub-Project A5 (Monitoring and Statistics), a web application has been developed to consolidate and rationalize the process of production of statistics relating to the Madrid and Hague systems operations, both for monitoring and general information purposes.  The new web application will offer online access to a broader range of statistical data, in addition to the monthly and annual statistics currently made available.  This application will also provide for searching facilities by criteria such as year, Office of origin and designated Contracting Party.  As of May 31, 2009, this application is being tested.  It should be in production as from September 2009.

10.	Under Sub-Project A6 (Office automation), which aims at integrating some additional administrative tasks into the MAPS/DMAPS system, new applications have been completed to replace manual or paper based processes by automated applications, such as the implementation of a new printing procedure using OMR (Optical Mark Recognition) technology, the automation of the certified e-mail notification system and the automated creation of certified copies of Hague recordings.

11.	Under Sub-Project A7 (IMAPS enhancements), the work done has made it possible, since May 2009, to export documents in PDF format via a web service, allowing better efficiency through improved indexing functions and printing functions.  Other developments are on-going, such as the creation of a means to store PDF documents in IMAPS and the planned importation of documents, including faxes and emails, directly into the IMAPS system.

(b)	Expanding electronic business with offices, holders and representatives

12.	This goal will be achieved with the completion of Sub-Projects B1 to B6 and C5.  Some of these sub-projects are dependent on the completion of the implementation of SOA tools (under Sub-Project C3).  Nevertheless, wherever possible, their project development has started.

13.	Some of the functions of Sub-Projects B1, B2, and B3 will be developed and regrouped under a unique web application.  Based upon a WIPO User Center secured account access, holders and representatives will be able to manage and execute selected transactions on their Madrid portfolios electronically, via the Internet.  The first version of this web application will be available in the last quarter of 2009 and will be updated upon completion of the development of new web services in 2010.

14.	Under Sub-Project B1 (e-Payment;  e-Billing), an e-payment facility is now available on the web for regularizing the fees to be paid for any transaction under the Madrid or Hague procedures.  Payment can be made via credit card or current account.

15.	Under Sub-Project B5 (e-Communication:  WIPO ( Holders/Representatives), an electronic version of the WIPO Gazette of International Marks was introduced with effect from February 5, 2009 and replaces the paper version of the Gazette – allowing savings for an amount of 200,000 Swiss francs to be realized in 2009.  This adds to earlier achievements under this sub-project, including the introduction of a certified e-mail notification system and several enhancements to the ROMARIN database (such as, the indication, since July 2008, where appropriate, that a refusal period has expired and the International Bureau has not recorded any notification of provisional refusal from the Office of a Contracting Party designated in a given registration;  and the inclusion in ROMARIN of PDF copies of grants of protection, provisional refusals and final decisions, as from January 2009).  Sub-Project B5 is now completed.

(c)	Laying the foundations for modification of the system

16.	As indicated in the previous status report (document MM/A/40/3), a series of technical sub-projects of Phase I of the IT Modernization Program is aimed at laying the foundations for modification of the system – in particular, Sub-Projects C2 and C3 – which set the architectural basis for the further development of the IT system – and Sub-Project C4 – which aims to run the current MAPS/DMAPS application on a new hardware platform and, thus, achieve substantial savings in operational costs of running the MAPS/DMAPS systems.

17.	Progress with the implementation of Sub-Projects C2, C3 and C4 has been hampered by unforeseen difficulties.  A fundamental assumption of Phase I of the IT Modernization Program was the rapid identification and engagement of external consultants with extensive ADABAS/Natural experience, who could liberate the WIPO staff experts from their current operational responsibilities.  This was in recognition of the fact that considerable Madrid and Hague system business knowledge had been acquired by the WIPO staff members making up the IT team responsible for the ongoing maintenance and support of MAPS and DMAPS since 1996.  For efficiency reasons, the same WIPO staff members had, therefore, better be assigned to lead the specific IT Modernization Program sub-projects and liberated from the maintenance and support responsibilities for the duration of the IT Modernization Program.  However, the process of identifying and engaging suitably qualified consultants with ADABAS/Natural experience has proven to be much more difficult than presumed.  Indeed, to date, only two such consultants could be identified and engaged.

(i)	Architectural basis – implementing a SOA platform

18.	When the previous status report was issued (document MM/A/40/3), the base architectural level of SOA required for the project had been established and the requirements of the request for proposals (“RFPs”) – that would result in the selection of the SOA tools to be implemented – were being written (under Sub-Project C2).  Since then, the RFPs have been issued, and the responses have been evaluated.  At the time of the preparation of this document, the successful bid was subject to validation by the Contracts Review Committee.  Implementation of Sub-Projects C2 and C3 is now scheduled to be completed by December 31, 2009.

(ii)	Savings in operational costs of running the MAPS/DMAPS systems

19.	This goal will be achieved with the completion of Sub-Project C4 – Downsizing to UNIX.  Under this sub-project, the MAPS/DMAPS systems will be migrated from the IBM mainframe at the UN International Computer Center (“UNICC”) to a UNIX environment.  Furthermore, the technical capability will be built for underpinning the e-business strategic evolution as well as the future availability of MAPS/DMAPS 24 hours/day, seven days/week.

Due to a longer than expected period of negotiation and validation of the financial figures with the UNICC – to which the actual hosting of the UNIX environment will be outsourced –, the implementation of Sub-Project C4 has been delayed.  The migration process as such could only start in June 2009.  It is scheduled to be completed by October 2009.

20.	The delay in the launch of Sub-Project C4 has resulted in the rescheduling of some other sub-projects due to unresolvable human resource conflicts (see Annex II).  In addition, the delay will result in reduced savings in operational costs in 2009, which will partially affect the financing of Phase I activities (it is recalled that Phase I was to be partially financed from reduced expenditure in operation costs under Program 27 (i.e., Program 25 under the Revised Program and Budget for 2008/09) for an amount of 1.9 million Swiss francs).  However, the relevance of going ahead with this sub-project still remains, considering the reduced operational costs for the future.  The resulting operational savings will be realized in the 2010-2011 biennium.

21.	Details on the state of play for all sub-projects are reflected in Annex II.

PHASE I – BUDGET STATUS

22.	The following table and graphic reflect the status of commitments and expenditure concerning the implementation of the IT Modernization Program by the end of June 2009:

IV.	CALENDAR FOR ACHIEVING THE GOALS ESTABLISHED

Phase I

23.	Taking into account the status of implementation of the various sub-projects, it is now estimated that Phase I will be completed by the end of 2010, according to the calendar reflected in the graph below.

Phases II and III

24.	When approving the implementation of Phase I of the IT Modernization Program in September 2007, the Madrid and Hague Union Assemblies noted that the International Bureau would make concrete proposals concerning Phases II and III in due course.  Phase II

was tentatively scheduled for implementation in the years 2010 and 2011.  Implementation of Phase III would depend on further analysis on whether it would eventually prove to be necessary and, if so, when.

25.	The approach initially followed under the IT Modernization Program was to continue to use the ADABAS/Natural database and programming language, taking into account the high level of satisfaction that the MAPS and DMAPS system functionality enjoyed among users, in general.  Instead of focusing on a completely new system, the IT Modernization Program aimed to further maximize return on the original system development investment by:  (i) migrating MAPS and DMAPS to a more cost effective operation platform;  (ii) focusing on “web” enabling the MAPS and DMAPS application systems – i.e., opening the systems transactions that were hitherto available only internally and, therefore, increasing the benefits to Madrid Union Members, and holders and representatives alike;  and (iii) addressing the obvious inherent shortcomings that a mainframe system has in the manipulation of text in support of letter production, as well as in classification and translation related  activities.

26.	As indicated at the outset of the IT Modernization Program (document MM/A/38/4, paragraph 29), Phase II would involve partial migration of Natural interactive programs to Java – Sub-Project C8 – and further development of the electronic publication subsystem – Sub-Project C10.  Phase III – which would result in the overall migration to a new technical environment resulting in the removal of ADABAS/Natural technologies (Sub-Projects C9 and C11) – was considered to be optional at that time.

27.	However, as already mentioned above, the International Bureau has had great difficulties in identifying consultants with extensive ADABAS/Natural skills, and ADABAS and Natural technologies would appear to be experiencing a rapid decline in the market place.  It is a fact that it is nearly impossible to locate staff sufficiently skilled in these technologies.

28.	Such recruitment difficulties have led the International Bureau to reflect upon the wisdom of continuing to have the Madrid and Hague operations dependant upon technologies for which it is clear that the level of skilled staff availability in the market place is dangerously low and the situation is unlikely to improve.  The conclusion of the International Bureau is that the risks associated with these systems remaining dependant upon ADABAS and Natural are too high and that mitigation measures need to be introduced.

29.	Consequently, implementation of Phase III as early as possible has become the most realistic option in the view of the International Bureau.

30.	On the basis of the information available to date, the International Bureau estimates that Phases II and III could be implemented according to the calendar reflected in the graph below.

V.	IMPLEMENTATION MODALITIES FOR PHASES II AND III

31.	One possible option for the implementation of Phases II and III would be to rely on in-house developments using consultants or third party contractors.  However, the costs associated with this approach may require reconfirmation considering the estimates were included in the consultancy report prepared by Sogeti S.A. Switzerland in the summer of 2007 in the run-up to the initiation of the IT Modernization Program.  In addition, there would also be an added element of risk due to the size and complexity of the redevelopment effort in a technology that internal staff are not familiar with.

32.	When considering the modalities for executing Phases II and III, there are a number of options relating to the final technical architecture that also need to be considered.  One option would be to establish an Oracle/Java environment identical (or similar) to the new PCT technical architecture. Another option would be to establish a Microsoft .NET environment.  The advantages of following the PCT lead in using Oracle/Java would mean that a single technical environment would from that time harbor all WIPO’s major business application software, with all the economies of scale that a single architecture would imply.  The disadvantage of following the PCT lead in using Oracle/Java would probably be cost, since Microsoft .NET system developments are generally less costly to initiate and to, subsequently, maintain.

33.	An alternative implementation approach would be to engage an external company to  convert the MAPS and DMAPS systems from ADABAS/Natural technology to an alternate technology to be determined by the company (Oracle/Java or Microsoft .NET, for example).  It should be noted that a significant portion of the technical, business specific complexity of MAPS and DMAPS is the bespoke workflow system that is integrated into the technical

solution.  Since Phase I of the IT Modernization Program includes the introduction of standard workflow tools (Business Processing Modules or BPM), any MAPS and DMAPS conversion exercise would be exclusive of the conversion of its bespoke work flow functionality.

VI.	RECOMMENDED APPROACH FOR PHASES II AND III

34.	For the implementation of Phases II and III, the International Bureau recommends that an open international tender be conducted with a view to selecting a company that would:

    - undertake a technical assessment of  the MAPS and DMAPS application systems and databases for the purposes of converting them into a new technical architecture;

    - propose an appropriate target technical architecture;  and

    - prepare a fixed price offer for the conversion of MAPS and DMAPS application software and data to the proposed new technical architecture, including the execution of subsequent system testing and the establishment of systems performance benchmarks, together with an appropriate warranty period.

35.	The longer term operational support of the converted solution would be modeled upon the successful approach currently in place for WIPO’s ERP systems – i.e., contracts would be concluded with an external partner for the ongoing development of the solution.  Such contracts would be administered by a core internal team of technical experts with strong business knowledge.  The internal team would be responsible for the day to day operation of the system and minor enhancements.

36.	The International Bureau is confident that the costs of following the approach recommended in paragraph 34, above would be well within the original cost estimates for Phases II and III (namely, 1.943 million Swiss francs and 8.292 million Swiss francs). The International Bureau is also confident that the proposal included in paragraph 35, above for ongoing support of the technical solution would be in line with industry practice as successfully demonstrated in the support model for WIPO’s ERP systems.

VII.	FINANCING OF PHASES I, II AND III

Remainder of Phase I

37.	As recalled in paragraph 3, above, a budget of 5.028 million Swiss francs was approved for the implementation of Phase I of the IT Modernization Program in 2008-2009.  However, as a result of the delays in the implementation of the program, as explained earlier in this document, only some 3.524 million Swiss francs will have been spent by the end of 2009.  Most of the remainder 1.504 million Swiss francs (most precisely, an estimated amount of 1.495 million Swiss francs) would still be needed for the purpose of completing the implementation of Phase I in 2010.

38.	Financing of the 3.524 million Swiss francs to be spent in 2008-2009 is expected to come from the following sources:  1.45 million Swiss francs from the Revised Program and Budget for 2008/09 (including 1 million Swiss francs from Program 6 and 0.45 million Swiss francs from Program 25);  2.074 million Swiss francs from the Madrid Union reserve set aside for this purpose.

39.	Financing of the 1.495 million Swiss francs currently estimated to be needed for completing the implementation of Phase I in 2010 is proposed to be financed from the Madrid Union Reserve Fund, as indicated in paragraph 49, below.

Phase II

40.	As indicated in document MM/A/38/4, the implementation of Phase II of the IT Modernization Program – to be undertaken in 2010/11 – would amount to an estimated cost of 1.943 million Swiss francs, to be shared between the Madrid Union (1,432,000 Swiss francs) and the Hague Union (511,000 Swiss francs).

41.	The Madrid Union’s share (1,432,000 Swiss francs) is proposed to be financed from the Madrid Union Reserve Fund, as indicated in paragraph 49, below.  Subject to the approval of the Assemblies of the PCT Union and the Hague Union, the part to be paid by the Hague Union (511,000 Swiss francs) would be financed from the PCT Reserve Fund, based on the understanding that that amount shall be reimbursed by the Hague Union to the PCT Union as soon as the level of reserves of the Hague Union Reserve Fund so allows.

Phase III

42.	As indicated in document MM/A/38/4, the estimated investment cost of Phase III, i.e. 8.292 million Swiss francs, would also be shared between the budgets of the Madrid Union (5,804,400 Swiss francs) and the Hague Union (2,487,600 Swiss francs).

43.	The part to be paid by the Madrid Union (5,804,400 Swiss francs) is proposed to be financed from the Madrid Union Reserve Fund, as indicated in paragraph 49, below.  Subject to the approval of the Assemblies of the PCT Union and the Hague Union, the part to be paid by the Hague Union (2,487,600 Swiss francs) would be financed from the PCT Reserve Fund, based on the understanding that that amount shall be reimbursed by the Hague Union to the PCT Union as soon as the level of reserves of the Hague Union Reserve Fund so allows.

Allocation of Funds from the Madrid Union Reserve and Working Capital Funds (RWCF)

44.	As indicated in paragraph 4, above, it is recalled that, in 2007, along with approving the implementation of Phase I of the IT Modernization Program, the Madrid Union Assembly also approved that any amount of the surplus generated by the Madrid Union budget by the end of 2007 exceeding the amount necessary to reach the target level of reserves (25 per cent of the estimated biennial expenditure in the 2008/09 biennium (PBE factor)) be kept within the Madrid Union RWCF with a view to contributing to the financing of subsequent stages of the IT Modernization Program.

45.	By December 31, 2007, the budget of the Madrid Union in 2006/07 had generated a surplus of 24.5 million Swiss francs, bringing the total level of reserves under the Madrid Union RWCF to an amount of 41.773 million Swiss francs.  This amount was re-stated under the methodology approved by Member States, to an amount of 41.510 million Swiss francs as at January 1, 2008.

46.	In the Revised Program and Budget for the 2008/09 biennium, approved by the Assemblies of WIPO Member States in December 2008, the Madrid Union budget was foreseen to have a deficit of 124,000 Swiss francs for the 2008/09 biennium.  The level of the Madrid Union RWCF was, consequently, established at 41.386 million Swiss francs

(41.510 – 0.124 = 41.386) as at the end of 2009.  Meanwhile, the Madrid Union RWCF target level for 2008/09 (25 per cent of the estimated biennial expenditure (PBE factor)) was established at 26.587 million Swiss francs (including the Working Capital Fund of 2 million Swiss francs).

47.	Also in December 2008, the Assemblies of WIPO Member States approved the allocation of an amount of 2.644 million Swiss francs from the Madrid Union RWCF to cover the Madrid Union’s share of a series of projects (security, IPSAS/FRR, etc.) approved by the Assemblies on that occasion.

48.	As explained in paragraph 38, above, it is expected that by the end of 2009, an amount of 2.074 million Swiss francs, financed from the Madrid Union RWCF, will have been spent in the implementation of Phase I of the IT Modernization Program in the 2008/09 biennium, as approved by the Madrid Union Assembly in 2007 (see, also, paragraph 3, above).

49.	Summarizing, it is expected that, at the end of 2009, some 10.081 million Swiss francs (41.386 – (26.587 + 2.644 + 2.074) = 10.081) will remain available within the Madrid Union RWCF.  As decided by the Madrid Union Assembly in 2007, those funds have been set aside to contribute to the financing of the subsequent stages of the IT Modernization Program.  As indicated in paragraphs 39, 41 and 43, above, the Madrid Union’s share in the financing necessary to implement the remainder of Phase I and Phases II and III of the IT Modernization Program in the 2010/11 biennium has been estimated at a total amount of 8.731 million Swiss francs (1.495 + 1.432 + 5.804 = 8.731).  It is therefore proposed to allocate such an amount of 8.731 million Swiss francs from the Madrid Union RWCF to cover that share.

50.	The Assembly is invited to:

- take note of the status of implementation of Phase I of the IT modernization program, as described in paragraphs 5 to 22 and Annex II of the current document;

- approve the implementation of the remainder of Phase I and of Phases II and III of the IT modernization program within the 2010/11 biennium, as proposed in  paragraphs 23, 30 and 34 to 43 of the current document;

- approve the financing of the remainder of Phase I and Phases II and III of the IT modernization program as proposed in paragraph 49 of the current document.

## Table 1:  Internal Operation

| Seq. | Project | Description | Category |
| --- | --- | --- | --- |
| A1 | Translation | Update translation tools to replace in-house translation tools with commercial ones. | Operational |
| A2 | Classification | Update Nice classification tools by integrating database of accepted goods and services into classification procedure. Develop a web application to assist users in composing lists. | Operational |
| A3 | Irregularity Letters and Notifications | Update the letter generation process to produce more understandable documents. | Operational |
| A4 | Trademark Latest Status | Create tools to show the goods and services protected within a given designated Contracting Party, and show how these change over time. | Operational |
| A5 | Monitoring and Statistics | Create tools to monitor and analyze operational processes. Create statistics for internal and external use. | Analytical |
| A6 | Office Automation | Integrate internal administrative tasks into the MAPS/IMAPS system, e.g., importing Word documents, e-mails, etc. directly into MAPS/IMAPS. | Operational |
| A7 | IMAPS Enhancements | IMAPS enhancements (e.g., search capabilities, new document formats, tighter integration with MAPS, …). | Operational |

## Table 2:  External Communication

| Seq. | Project | Description | Category |
| --- | --- | --- | --- |
| B1 | e-Payment, e-Billing | Create e-Billing (for extracts from the International Register) and e-Payment (for other transactions) for holders. | e-Business |
| B2 | e-Modification | Allow holders to submit transactions electronically and to further automate their processing within MAPS. | e-Business |
| B3 | e-Status | Allow holders to monitor the status of their communications to WIPO. | e-Business |
| B4 | Electronic Communication: Offices → WIPO | Enhance the transmission of information from national or regional offices to WIPO. | e-Business |
| B5 | Electronic Communication: WIPO → Holders/Representatives | Enhance the transmission of information from WIPO to holders and representatives. | e-Business |
| B6 | Electronic Communication: WIPO → Offices | Create tools that enhance collaboration between WIPO and national or regional offices with respect to the international procedure. | e-Business |

Table 3:  Governance and Technical

| Seq. | Project | Description | Category |
| --- | --- | --- | --- |
| C1 | Project Organization and Change Management | Put procedures into place which will facilitate the implementation of these projects. | Governance |
| C2 | Requests for Proposal and POC | Requests for Proposal (tenders) and Proof of Concept of technical solution. | Governance |
| C3 | SOA and Tools | Create the IT architecture (SOA) and provide the necessary tools for its use. | Architecture |
| C4 | Downsizing to Unix | Migrate MAPS and DMAPS from the UNICC mainframe to a UNIX environment. | Downsizing |
| C5 | Pilot with an Office | Pilot project with a single national office based on direct access to MAPS. (SOA+BPM+e-Business +Portal+RIA). | Conversion |
| C6 | Complete Architecture + BPM + Middleware | Adapt the IT architecture and BPM processes based on experience with Pilot (C5) to allow expansion to other interested offices. | Conversion |
| C7 | DBMS and Technical Enhancements | Improve the database design of MAPS and resolve any technical issues. | Conversion |

| Seq. | Project | Description | Category |
| --- | --- | --- | --- |
| C8 | Remaining BPM, Portal and RIA | Migrate business logic from Natural to Java, but retain Adabas. | Conversion |
| C9 | Remaining Interactive Web Services | If needed, define processes and develop a new user interface with common technology for WIPO and national or regional offices. | Conversion |
| C10 | Publication | Modernize the publication process including the replacement of the legacy Visual Basic programs. | Architecture |
| C11 | Remaining Java / Oracle Conversion | Migrate the remaining Natural /Adabas programs to Java/Oracle if and when needed, but not before 2010. | Conversion |

|  | A1 | Translation |
| --- | --- | --- |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 124,500 | 56,566 | 131,094 | -- | 67,934 | (6,594) | (6,594) |
| Description |  | Update translation tools to replace in-house translation tools with commercial ones |
| Benefits |  | More automation, reduced costs, improved quality |
| Current status |  | Application for automating the translation of overrides using the translation of the basic list is under test (Beta Test) as of May 31, 2009 |
|  | A2 | Classification |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 124,500 | 78,113 | 114,294 | -- | 46,387 | 10,206 | 10,206 |
| Description |  | Update Nice classification tools by integrating database of accepted goods and services into classification procedure. Develop a web application to assist users in composing lists. |
| Benefits |  | Database of validated terms available on the Web, that helps users of the Madrid system pre-validating their list of goods and services |
|  |  | Decreased time processing and automated translation for pre-validated lists |
| Current status |  | Prototype of the E-Classification application is available on the Intranet and under test as of May 2009 |
|  | A3 | Irregularity Letters and Notifications |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 480,000 | 23,035 | 235,060 | 280,000 | 456,965 | 244,940 | (35,060) |
| Description |  | Update the letter generation process to produce more understandable documents |
| Benefits |  | Producing more comprehensive letters |
| Current status |  | A working group is working on the requirements |
|  | A4 | Trademark Last Status |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 240,000 | 11,517 | 117,530 | 135,000 | 228,483 | 122,470 | (12,530) |
| Description |  | Create tools to show the goods and services protected within a given designated Contracting Party, and show how these change over time |
| Benefits |  | Better and clearer status of trademark within a given designated Contracting Party |
| Current status |  | A working group is working on the modifications, from the examination policy to the IT tools, required to determine the Goods and Services that have effect in given designated Contracting Party |
|  | A5 | Monitoring and Statistics |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 340,000 | 16,316 | 87,984 | -- | 323,684 | 252,016 | 252,016 |
| Description |  | Create tools to monitor and analyze operational processes. Create statistics for internal and external use |
| Benefits |  | Access to statistics from Intranet and Internet |
| Current status |  | Prototype of the Web application is available on the Intranet and under test as of May 10, 2009 |
|  | A6 | Office Automation |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 48,000 | 31,803 | 51,506 | -- | 16,197 | (3,506) | (3,506) |
| Description |  | Integrate internal administrative tasks into the MAPS/IMAPS system |
| Benefits |  | Less manual procedure, less paper based processing |
| Current status |  | New printing procedure using OMR technology: completed |
|  |  | Automation of the certified email system: completed |
|  |  | Automation of the creation of certified copies of Hague applications: completed |
|  | A7 | IMAPS Enhancements |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 48,000 | 16,221 | 51,424 | -- | 31,779 | (3,424) | (3,424) |
| Description |  | IMAPS enhancements (e.g., search capabilities, new document formats, tighter integration with MAPS, …) |
| Benefits |  | Additional functions for users |
| Current status |  | Export in PDF format for Tiff document: completed |
|  |  | New indexing and printing functions: completed |
|  |  | Management of native PDF format inside IMAPS: on-going |

|  | B1 | e-Payment, e-Billing |
| --- | --- | --- |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 240,000 | 11,517 | 117,530 | 125,000 | 228,483 | 122,470 | (2,530) |
| Description |  | Create e-Billing (for extracts from the International Register) and e-Payment (for other transactions) for Holders |
| Benefits |  | E-payment facility for users of the Madrid system |
|  |  | Reduce processing time for Finance |
| Current status |  | E-payment, by credit card or current account, is available on the Web site for paying fees upon reception of an irregularity letter |
|  |  | E-billing for extracts and e-payment of standard fees is under study |
|  |  | Additional E-Business functions from B1 will be implemented through a common project where holders and representatives will be able to manage and execute selected transactions on their Madrid portfolios electronically, via the Internet |
|  | B2 | e-Modification |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 336,000 | 16,124 | 124,542 | 215,000 | 319,876 | 211,458 | (3,542) |
| Description |  | Allow holders to submit transactions electronically and to further automate their processing within MAPS |
| Benefits |  | Reducing processing time for users |
|  |  | Reducing workload (Mail processing team) |
| Current status |  | E-Business functions from B2 will be implemented through a common project where holders and representatives will be able to manage and execute selected transactions on their Madrid portfolios electronically, via the Internet |
|  | B3 | e-Status |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 240,000 | 11,517 | 137,530 | 100,000 | 228,483 | 102,470 | 2,470 |
| Description |  | Allow holders to monitor the status of their communications to WIPO |
| Benefits |  | Better communication to holders |
|  |  | Decreasing requests receive from holders |
| Current status |  | E-Business functions from B3 will be implemented through a common project where holders and representatives will be able to manage and execute selected transactions on their Madrid portfolios electronically, via the Internet |
|  | B4 | Electronic Communication: Offices -> WIPO |
|  |  | Budget, description and current status included under C5 |
|  | B5 | Electronic Communication : WIPO -> Holders/Representatives |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 120,000 | 103,509 | 126,515 | -- | 16,491 | (6,515) | (6,515) |
| Description |  | Enhance the transmission of information from WIPO to holders and representatives |
| Benefits |  | Better communication to holders |
|  |  | Costs savings from paper less transmission |
| Current status |  | Gazette is now exclusively available via the Internet and has been enhanced with search functions |
|  |  | Notification of certain communications are now available via the internet (ROMARIN) |
|  |  | Notification of certain communications by certified email is now available |
|  | B6 | Electronic Communication: WIPO -> Offices |
|  |  | Budget, description and current status included under C5 |

|  | C1 | Project Organization and Change Management |
| --- | --- | --- |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 48,000 | 36,686 | 37,889 | 0 | 11,314 | 10,111 | 10,111 |
| Description |  | Put procedures into place which will facilitate the implementation of these projects |
| Benefits |  | Enabling the project to progress |
| Current Status |  | Completed Project office and Project Team in place |
|  | C2 | Requests for Proposal & POC |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 48,000 | 17,803 | 87,506 | -- | 30,197 | (39,506) | (39,506) |
| Description |  | Requests for Proposal (tenders) and Proof of Concept of technical solution. |
| Benefits |  | Providing hardware/software platform for the project and the hosting services for UNIX and SOA platform |
| Current status |  | Offers from bidders have been evaluated and the successful bid is currently subject to Contract Review Committee validation |
|  | C3 | SOA & Tools |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 72,000 | 16,705 | 105,509 | -- | 55,295 | (33,509) | (33,509) |
| Description |  | Create the IT architecture (SOA) and provide the necessary tools for its use |
| Benefits |  | Provides other projects with the tools required to be developed. |
| Current status |  | Offers from bidders for SOA tools are under final evaluation |
|  |  | Technical implementation will follow |
|  | C4 | Downsizing to Unix |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 1,529,875 | 109,133 | 1,625,843 | -- | 1,420,742 | (95,968) | (95,968) |
| Description |  | Migrate MAPS and DMAPS from the UNICC mainframe to a UNIX environment |
| Benefits |  | Reduce running costs of MAPS/DMAPS |
| Current status |  | Thorough analysis: competed |
|  |  | Detailed analysis: completed |
|  |  | Selection of consulting services fro the migration through an RFP: completed |
|  |  | New contract with ICC: completed |
|  |  | Technical implementation: started as of June 2009 |
|  | C5 | Pilot with an Office (includes B4 and B6) |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 599,200 | 28,755 | 323,766 | 300,000 | 570,445 | 275,434 | (24,566) |
| Description |  | Pilot project with a single national office based on direct access to MAPS. (SOA+BPM +e-Business+Portal +RIA) |
| Benefits |  | Implementing, using, validating and learning new technology (SOA+BPM +e-Business+Portal +RIA) |
| Current status |  | Depending on the completion of C2 and C3. It will start as of September 1, 2009 |
|  | C6 | Complete Architecture + BPM + Middleware |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 150,000 | 7,198 | 10,956 | 140,000 | 142,802 | 139,044 | (956) |
| Description |  | Adapt the IT architecture and BPM processes based on experience with Pilot (C5) to allow expansion to other interested offices |
| Benefits |  | allow various stakeholders to benefit from the new SOA tools |
| Current status |  | Will start upon completion of C2, C3 and C5 |
|  | C7 | DBMS & Technical Enhancements |
|  |  | Initial Budget | Total Expenditure | Total Earmarked 2009 | Total Futures 2010 | Balance Based on Expenditures | Balance Based on Earmarked 2009 | Balance Based on 2009 + 2010 |
| Budget |  | 240,000 | 11,517 | 37,530 | 200,000 | 228,483 | 202,470 | 2,470 |
| Description |  | Improve the database design of MAPS and resolve any technical issues |
| Benefits |  | Adapt the database to new tools |
| Current status |  | Will start upon completion of C2, C3 and C5 |

[End of Annex and of document]

# Footnotes

Paragraphs 35, 36 and 42 of document MM/A/38/4, and paragraph 14 of document H/A/24/2.

Financed from the Madrid Union budget for an amount of an estimated 2.441 million Swiss francs and from the Hague Union budget for an amount of an estimated 459 thousand Swiss francs.

Document MM/A/38/6, paragraph 41.

For the content of these sub-projects, reference is made to Annex I, Table 1.

For the content of these sub-projects, reference is made to Annex I, Table 2.

Service-Oriented Architecture:  an architecture that uses loosely coupled services to support the requirements of business processes and users.

Document MM/A/38/4, paragraph 46(iii).

The International Bureau is currently in the process of decommissioning its legacy PCT application systems, which are also ADABAS/Natural dependant, and which have been replaced with a modern three tier Oracle/Java technical solution that has been the result of years of development effort.

The re-statement is the result of the application of the adjusted income and expenditure allocation methodology (see Annex IV of the Revised Program and Budget for 2008/09), as approved by Member States as part of the 2008/09 Program and Budget.

Proof of Concept:  verifying that the proposed technical architecture performs according to specifications.

Service-Oriented Architecture:  an architecture that uses loosely coupled services to support the requirements of business processes and users.

Business Process Management.

Portal:  a Web interface which provides individualized access to users based on their security profile.

Rich Internet Application:  a Web application that has the features and functionality of traditional desktop applications.

Database Management System.