| WORLD INTELLECTUAL PROPERTY ORGANIZATION GENEVA AUDIT OF THE BUILDING PROJECT for the creation of a new administrative building with a car park, additional storage areas and a conference room |
| --- |
| Report by the External Auditor to the General Assembly |
|  | Reg. No. 2187/944.00.1.13 - 01 nede/reda Berne, June 24, 2002 |

(NE PAS SUPPRIMER CETTE LIGNE)

## TABLE OF CONTENTS

PART I

## Summary and conclusion

1	Summary

## Terms of reference	        (paragraphs)	  1-2

1.1	Verification of needs	
	How did the specification evolve over time? 	  9-12

What are the present terms of reference?	13-16

1.2	Evaluation of the November 2001 Final Project
	Does the future building meet WIPO’s needs?	17-21
	November 2001 final project	22-35
	Are the planned costs reliable?	36-44

1.3	Assessment of the profitability of a conference room	
	Is a conference room profitable at all?	45-47
	What if any is the variation in the number of participants
                  in WIPO meetings?	48-49
	What would be the ideal capacity for the conference room ?	50-51
	Should it be possible to divide the room ?	52
	What amount would have to be invested ?	53
	Market survey	54

1.4	Verification of the various estimates	
	How was it that a budget of 82.5 million became an estimate
                 of 180 million ?	55-62

1.5	Conclusion	63-76

PART II

Report and Supporting Arguments

SIA: 	Swiss Association of Engineers and Architects

GFA: 	Gross Floor Area

CFC: 	Code des frais de construction (construction costs broken down into 9 groups)

## 2	General

2.1	Terms of reference	77-79

2.2	Object of the audit

2.3	Information and Documentation	80-82

2.4	Development and structure of audit process	83

## 3	Appointment of groups of experts

3.1	Documentation submitted for study	84

3.2	Structure of the experts’ terms of reference	85-90

3.3	Call for tenders	91

3.4	Budget envelope	92

  - Program of analysis

## 4	Analysis

4.1	Definition of framework of analysis	94-101

4.2	Mission	102

4.3	Context and WIPO objectives	103-109

4.4	Changes in needs and buildings inventory

4.4.1	Changes in needs between 1993 and 2001	110-113
4.4.2	Buildings inventory	114

4.5	Latest staffing forecasts	115-123

4.6	Present terms of reference

4.6.1	Staff	124-126
4.6.2	Parking places	127-131
4.6.3	Storage areas	132-133

4.7	Evolution of the projects	
4.7.1	History	134-142
4.7.2	Net comparative area of the various projects	143
4.7.3	SIA volume of the various projects	144
4.7.4	Changes to the specification since 1997	145-150
4.7.5	Changes to the programs between the Competitions and the

November 2001final project	151-152

4.8	Analysis of the final project	
4.8.1	Project review	153-171
4.8.1.1	Fulfilment of the specification	172-180
4.8.2 	Civil engineer	181-188
4.8.3	Heating, ventilation and air conditioning engineer (CVC)	189-194
4.8.4	Building doctor	195-201
4.8.5	Plumbing engineer	202-205
4.8.6	Electrical engineer	206-219
4.8.7	Sound engineer	220-228

4.9	Analysis of costs	229-233
4.9.1	Comparison of prices per m3 SIA and m2 GFA, all CFC combined	234-239
4.9.2	Comparison of prices per m3 SIA and m2 GFA, CFC 2	240-243
4.9.3	Comparison of prices per m3 SIA and m2 GFA for the conference

room	244-247
4.9.4	Risks	248-252
4.9.5	Ratios per working place	253-259

  - Conference room

4.10.1	Profitability	260-269

4.10.2	Justification of future needs	270-281

5	Project organization	282-287

6	Inventory of savings and other technical solutions

6.1	Technical solutions	288-292
6.2	Possible savings	293-298

PART III

Annexes

PART IV

References

## PART I

## Summary and conclusion

## 1.	SUMMARY

## Terms of reference

- The World Intellectual Property Organization, which has its headquarters in Geneva, has plans to erect a new administrative building on its site with a car park, additional storage areas and a conference room.  The scale of the increase in the construction costs bore so little relation to the allocated budget that the WIPO Program and Budget Committee recommended to the General Assembly of September 24, 2001:

- “(i)  to request the Federal Audit Office of the Swiss Confederation, as the External Auditor of WIPO, or other external experts [to be identified by the External Auditor], for those areas which the External Auditor judges not to be within his competence, [in consultation with the Chairperson of the Program and Budget Committee and regional coordinators], to conduct an evaluation of the project of the construction of a new building, in cooperation with the International Bureau, the architect of the winning design and other relevant organizations as appropriate.

“(ii)  to propose to include in the mandate for the evaluation, the following terms of reference :

“(a)  updating the current and foreseeable business needs of the Organization, with special attention to the process of planning and needs assessment, to include :

- the impact of major investments, especially those in information technology, aimed at improving the efficiency of the Organization,

- the financial implications and [business case for a conference center, and the phrase] business case for a conference center, and

- an assessment of alternative solutions for technical facilities.

“(b)  assessing the building proposal in terms of its ability to achieve the Organization’s business objectives in a cost-effective way while providing the maximum possible value for money ;  and

“(c)  preparing a risk assessment, incorporating the financial implications for the Organization and the possibility of further increased costs to the project ;

“(iii)  to invite the External Auditor and the other external experts to present their respective reports in time for consideration by Program and Budget Committee in April 2002.”

- In order to conduct this evaluation in a manner consistent with the terms of reference given me, I arranged for two working groups to be set up composed of eight external experts (seven technical experts and one economist).  I entrusted a colleague from the Federal Audit Office to direct the process, coordinate the two working groups and write the final report.

- The process of analysis and the planning of the evaluation was submitted to the members of the WIPO management and to the representatives of regional groups on December 13, 2001.  The analysis began on February 20, 2002, and the final report was delivered on June 24, 2002, as the program required.  The evaluation was therefore conducted in a relatively short time, considering that the external experts were not operational until after the call for tenders, at the end of February 2002.

- The terms of reference of the experts were organized under four headings:

- Verification of needs

- Evaluation of the November 2001 final project

- Evaluation of the profitability of a conference room

- Verification of the various estimates

- The observations and thoughts set down in this report reflect the general view of the advisers and the External Auditor, reached on the basis of the literature and information provided by WIPO.

- The economy measures mentioned are indicative only, and of course will depend on the evolution of the project and the alternatives considered.

- The report has been divided into four parts as follows for ease of reading and accessibility:

- Part I	Summary of the report and conclusion

- Part II	Report and supporting arguments

- Part III	Annexes

- Part IV	References

The numbering of the tables and diagrams corresponds to that of the advisers’ reports.

1.1	VERIFICATION OF NEEDS

How did the specification evolve over time ?

- The specification evolved according to staffing forecasts and the capacity of the buildings rented or owned by WIPO.  Thus, between 1994 and 2000, the staffing forecasts for 2005 increased by 36% (from 1,152 to 1,565), for 2006 by 29% (from 1,275 to 1,643) and for 2007 by 31% (from 1,361 to 1,778).  The latest staffing forecasts contained in the WIPO report (Report 1, Needs for Office Space and Parking, April 11, 2002) are structured according to an outlook that is both optimistic and more pessimistic.  For 2007, for instance, the working places requirement, including a five per cent reserve, may be summarized as 1,867 places in the optimistic forecast and 1,622 places in the pessimistic forecast.

- The forecasts made since 2000 show a considerable increase in staff strength for 2007 in spite of the introduction of new IT facilities (IMPACT program).  According to a study carried out by De Loitte and Touche in 1998, a 23 per cent staff saving should be achieved on the introduction of the program.  That corresponds to a reduction by 126 posts in 2007, assuming optimistic growth.

- What is more, the buildings inventory speaks of 1,589 working places available to WIPO today, to which 450 places under construction in the former WMO building will be added in 2003, making a total of 2,039 places, including 1,010 (50%) owned by WIPO.

- A figure of 1,028 parking places was also found, to which 180 places under construction would be added, making a total of 1,208 parking places available (including 419 (30%) owned by WIPO).  The need for 280 additional parking places to be located in an extension to the present headquarters car park, mentioned in document WO/GA/23/5 of July 1998, is not evident.  Moreover, the reassignment of that parking area for use as storage space, as mentioned in the plans of the final project, makes for some confusion.

What are the present terms of reference ?

- In the light of the latest forecast made by WIPO (Report 1, Needs for Office Space and Parking, April 11, 2002), the terms of reference for 2007 may be summarized as follows:

- According to the optimistic forecasts, 857 working places (1,867 minus 1,010) are necessary.  It will not be possible to meet this need in the construction of the new building, but continued rental of the greater part of the Procter & Gamble (P&G) building, with its 430 places, brings the number of working places necessary in the new building down to 427 (857 minus 430).

- The pessimistic forecast presupposes WIPO discontinuing the rental of the P&G building and accommodating all its staff on its own premises after the construction of the new administrative building.  The need for working places would then be 612 (1,622 minus 1,010).

The need for working places is therefore between 427 and 612, which corresponds to an average demand for 500

- The need for parking places in the new building is estimated at between 514 and 603 (see paragraphs 127-131 for the details).  However, the ratio of 80 parking places to 100 staff seems extremely high on an urban site.  By way of comparison, the new WMO building has a 410-place car park for a building with 625 working places, corresponding to a 66:100 parking place-working place ratio.  If one alters the ratio to 66:100, the result is a 265-place requirement for the optimistic forecast and 387 places for the pessimistic forecast (with the P&G building no longer being rented), which seems more realistic.

- The storage space requirement is difficult to quantify.  Document WO/GA/23/5 of July 29, 1998, speaks of an extension of the present WIPO car park that would allow 280 places to be added for delegates and visitors at conference times.  This car park, although mentioned in the introduction to Competition No. 2, is not described in terms of area and capacity.  What is more, it does not appear in the winning design.  However, the areas are found in the final project, but their intended use is put as storage, whereas the need for this kind of area is not specified anywhere.  I infer from this that the storage area could one day be converted into a car park, thereby acceding to the requests of Member States.  Apart from that large area, storage needs (3,000 m2) are defined in the rules of Competition No. 2.  When they are present in Geneva, delegates attending WIPO conferences use other forms of transport (city buses and shuttle buses, taxis) rather than private cars.  The need to provide a dedicated car park for this category of temporary visitors has yet to be proved, and calls for study in greater depth.

- Summary of the terms of reference for 2007 :

|  | Optimistic forecast | Pessimistic forecast | Comments |
| --- | --- | --- | --- |
| Number of working places to be provided in the new building (incl. 5% reserve) | 427 | 612 | The optimistic forecast presupposes rental of the P&G building |
| Number of parking places | 265 | 387 | (parking space 66% of staff numbers) |
| Storage areas | 3,000 m2 | Competition No.°2 |
| Conference room | 600 places |  |

1.2	EVALUATION OF THE NOVEMBER 2001 FINAL PROJECT

Does the future building meet WIPO’s needs?

- Analysis of the plans of the final project leads one to believe that the actual capacity of the new office complex is in the range of 429 to 554 working places, depending on the potential for office space compression.  The need for working places would thus be met by the optimistic figure as WIPO continues to rent the P&G building.  On the other hand the terms of reference are not met by the pessimistic figure, which would result in a shortfall of 60 working places.

- It seems to us on the whole that the present project makes use of the maximum capacity available under the PLQ (local district plan) to accommodate a small number of working places.  Given WIPO’s potential for growth, it would seem more appropriate to provide for a higher degree of office space compression, in the knowledge that some of that potential might not be made use of until a later date.  This comment should be placed in the context of the excessively large areas on the ground and mezzanine floors which cramp the project.

- It should be pointed out that closer studies of the plans of the final project reveal a capacity of about 1,000 office modules of 7m2, whereas the specification of the competition called for 1,285.  The number of modules has thus been reduced by 285, which corresponds to a potential shortfall of about 140 offices at 14m2.  There is no document that affords any explanation of this step.

- Storage areas.  These areas come to a total of 6,185 m2 more than the 3,000 m2 already set down in the specification (see paragraph 16):  archive areas of 1,'700 m2 have been noted and storage areas of 4,485 m2;  in my opinion those additional areas can only be explained by a future reassignment of certain additional storage areas as parking space (subject to acceptance by the Geneva authorities), in response therefore to the original demands of Member States.

- Parking places.  As mentioned above, the number of parking places to be accommodated in the new complex should be between 265 (optimistic figure) and 387 (pessimistic figure).  For the record, it should be remembered that the high figure presupposes WIPO to rent the P&G building, which contains 275 parking places.  As the new complex provides for the addition of 280 places, the requirements corresponding to the optimistic figure would be covered, while in the case of the pessimistic figure there would be a shortfall of 107 places.  It should also be borne in mind that the calculation of parking places is the result of a reduction in the parking places-to-employees ratio from 80:100 (high for an urban site) to 66:100 (based on the WMO Geneva reference).  Without that reduction, the lack of parking places would be even more serious, regardless of the alternative adopted.

November 2001 final project

- My study relates to the November 2001 final project and cost estimate.  It is important to point out, however, that the status of the contributions by the technical contractors in November 2001 was out of phase with what is commonly known as the “final project”:  about half their contributions to the supposedly final project were still missing.  The real “final project” stage had been reached only by the architect, and even that did not apply to the conference room, which was at the pre-project stage.  The overall estimate that generally accompanies a final project was not available before March 2002, so I consider that the document submitted in November 2001 would constitute the basis for the advisers’ study.

- On analyzing the overall project, one notes that what are called the “secondary volumes” (car parks, storage areas, etc.) have become greater than the volumes set aside for “primary” needs (offices, conference room), although the latter were the original reason for which the building was to be constructed.  The tables below show how this situation has evolved since 1997, up to the 2001 final project.  The continuous, steady increase in “unproductive” areas (repositories, storage, etc.) in relation to useful areas, which we have noted in our analysis of the projects, puts a heavy strain on the final project.  Moreover, there is still some confusion regarding the need for an independent car park and independent storage areas.

- Table 6 bis’’’  Competition No.1, 1997
	             Allocation of gross floor area

25.  Table 6 bis” Competition No. 2, 1999

Allocation of gross floor area

26.  Table 6 bis.  Final project, November 2001
	            Allocation of gross floor area

- On an unspecified date in 2001, at WIPO’s request, the conference room was removed from the main volume calculation to become an independent feature located close to the present headquarters.  The volume of the new building remained the same after the removal.  As a result, the ground and mezzanine floor areas are out of proportion to their actual use, even if one considers what are called representative areas.  This substantially increases the area ratio (and the volume) per working place, and upsets the economics of the project.  The table below illustrates this observation, and shows clearly that the future WIPO complex has representative areas or areas without a clearly assigned purpose that are too large.  Conversely, the number of working places is too small for the given volume and area.

- Table 15.  SIA volume per working place :
(SIA : Swiss Association of Engineers and Architects)

- WIPO’s decision to remove the conference room and bring it closer to the present headquarters building was therefore not accompanied by a rearrangement of the areas so released.  The reduction in the “representative and public” areas or a reassignment of those areas as a reserve for working places would however make it possible to achieve ratios more readily comparable with those of the buildings of other international organizations.  The configuration of the car park would also benefit from a redesign to improve its use.

- The conference room gives the impression of conforming more to an architectural concept than to a specification.  To illustrate this, the present division of the room into 280 and 320 places is not consistent with the initial (competition) requirement of 150 and 450 places.  All the experts agree that the state of progress on this aspect of the job does not correspond to a “final project” but rather to a “pre-project.”  It is therefore important to effect the completion of the planning stage rapidly with the assistance of a specialist in conference room design.

- WIPO’s objectives specify among other things that the new building has to be “modern,” in other words that it has to incorporate the most up-to-date construction and information technology, be compatible with the environment and be energy efficient.  One is bound to observe that the technical concepts produced do not fulfil that requirement, apart from which the planners have not concerned themselves with the “Minergy” concept for the rational use of power in buildings.

- There are still a great many important choices to be made and decisions to be taken regarding electrical networks and CVCS (heating, ventilation, air conditioning and plumbing).  The documents relating to the overall estimate of March 28, 2002, which were consulted for information even though they do not form part of the terms of reference of this analysis, do not incline us to revise this opinion.  With a view to the continuation of the project, it does seem necessary to do more work on power, plumbing and electricity concerns in the light of the present level of technical know-how and with a view to achieving synergy with the present installation (subject to adherence to the overall costs in the November 2001 estimate).  There should moreover be greater coordination among the various contractors.

- As far as energy consumption on heating and cooling is concerned, even though the heat insulation of the buildings conforms to legal requirements, it has to be said that the project cannot be described as exemplary:  in fact the legal requirements are only just met as far as the administrative building is concerned, while the conference room actually falls 10% below them.  The large glazed areas on the façades and built into the ceilings of the common areas are certain to be a source of comfort problems in both winter and summer.  It is possible to remedy these problems with appropriate heating and cooling installations, but that would nevertheless make for higher installation and power costs:  given the large glazed areas, it has to be expected that the additional power consumption for heating and air conditioning will exceed 10%.

- The sound engineer considers that the entire “acoustic project” of the conference room, common areas and offices has to be redesigned according to the actual acoustic requirements of users, and that the “architectural project” should be modified accordingly.  According to him, the design of areas and volumes should first meet the acoustic requirements of users, with the architectural design being dealt with afterwards.

- In particular he points to the need for a reduction in the volume of the conference room by about 40%, in order to meet acoustic requirements.  Apart from that, the shape of the room is highly unsatisfactory with respect to visibility from the interpreters’ booths and from certain seats in the room.  It should be borne in mind that good visibility and good verbal comprehension go hand in hand.  Also, the acoustics between the individual offices of the administrative building and on the mezzanine areas overlooking the reception area seem inadequate.  Some work on the acoustics of the reception areas is necessary to remedy this problem.

Are the planned costs reliable?

For the purposes of comparison, we have seen fit to consider side by side the estimate for the November 2001 final project and both the estimates and final accounts of four comparable reference sites in the Geneva region.  The WMO and HCR buildings were chosen for their geographical nearness to the future complex (similarity of site and context), and also for their programs which are comparable to those of WIPO.  The Salle William Rappard in the WTO building is the only recent reference available for comparison, being of a size similar to that intended for WIPO.  Finally, the Du Pont de Nemours building has features (volume, inner reception areas, etc.) in common with the future complex, while at the same time serving for comparison with a private business.

- Table 10.  Comparison of m3 SIA prices per CFC (without fees) :
CFC:  Code des frais de construction (construction costs broken down into 9 groups)

Administrative building, additional storage area and conference room

- The planned costs at the final project stage correspond to the amounts paid for comparable work in Geneva.  I can therefore confirm the budget of 180 million francs as being a realistic package, even though some rebalancing seems necessary between various types of work:  The costs in the estimate for excavation (CFC 20) and for heating, ventilation and air conditioning installations (CFC 24) are above average.  Conversely, the costs associated with plumbing installations (CFC 25) and transport facilities (CFC 26) are lower than average.  CFC 22, which generally covers façades, is also very low.

- What is more, I am of the opinion that the volume and area of this design are too great in relation to the number of working places available.  That has the effect of increasing considerably the cost per working place and hence the overall cost of the project.  It would benefit the project as a whole if it were reviewed it from the point of view of optimum use of usable areas.

- Table 16.  Total cost per working place

- The civil engineering adviser says that the costs relating to the surrounds of excavation, the excavations themselves (CFC 20) and concrete and reinforced concrete structures (CFC 21) relating to the additional storage area have been over-valued by about 30%.  The project review adviser also confirms that an abnormally high cost of 707 francs per m3 has been noted;  it is customary to work with a figure closer to 500 francs per m3.

- The high cost (+ 43%) of the heating, ventilation and air conditioning plant (CFC 24) can be explained on the one hand by WIPO’s requirements and on the other by the relatively costly air conditioning concept chosen.

- The probable cost of the proposed electrical installations (CFC 23) is within the range of comparable values for other administrative buildings similar to the WIPO project.  That cost is relatively low, however, compared with other buildings of a high technical standard.  This is particularly true if one considers that the building in question should be a high-technology construction.  The actual overall cost, after a number of details have been dealt with, could be higher.

Table 12.	Conference room – Comparison of m3 SIA prices per CFC 
	(without fees)

Conference room :

- The cost analysis for the conference room shows that overall that the price per m3 is comparable to that of the Salle William Rappard.  In view of the high quality of that room, the amount of the estimate for the WIPO room seems adequate.  However, the uncertainty regarding the progress of that part of the project and the somewhat unclear intentions of the architects lead me to express reservations.  I draw WIPO’s attention to the fact that this part of the project is at a less advanced stage of development than the remainder, and as a result there is less precision in the costing.

- The degree of precision allowed by the Swiss (SIA) standards at the final project stage is
+/-10%.  We find that only the administrative building and the additional storage area (excluding relevant technical installations) meet that standard.  The other parts of the design (conference room, technical installations of the administrative building and additional storage areas) do not correspond to final project status but rather to pre-project status.  Consequently I have worked out that the allowable share of risk is +24 million francs instead of +18 million francs, according to Swiss standards, or +9 million francs according to market standards.

1.3	ASSESSMENT OF THE PROFITABILITY OF A CONFERENCE ROOM

Is a conference room profitable at all ?

- Calculations of the profitability of a conference room offering either 400 or 600 seats have shown that the annual operating cost would exceed the cost of renting external premises by 0.75 and 1.5 million francs respectively.  Consequently, the construction of a 400-seat or 600-seat conference room is not profitable.  From a strictly economic point of view, the option of not constructing a new conference room seems the most defensible among those proposed.

- Analysis of the options, with costs :

| Scenario | Room capacity (seats) | Investment in millions | Operating costs in millions *** | Rental costs in millions | Total in millions | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 0 | 0 | 0 | 0.75* (0.3 – 1)** | 0.75 | Present situation |
| 2 bis | 400 | 20 | 1.5 | 0.2 – 0.9 | 1.7 – 2.4 | Investment corrected from 15 to 20 million francs |
| 3 | 600 | 30 | 2.25 | 0 – 0.5 | 2.25 –2.75 | Final project |

*	Average annual cost of external rentals in 2000 and 2001.
** 	Costs +/- identical to option 2, as major conferences are spread over a large number of days and involve the use
       of more than 400 seats.
*** 	Amortization has been calculated at 3.25% over 40 years.

- The following emerges from examination of the options summarized in the table above:

| 400-seat room : (15 million) | When considered alongside a comparable building such as the Salle William Rappard, the budget of 15 million francs approved by the Member States is not realistic. It would be better to assume an investment of 20 million francs. |
| --- | --- |

| 400-seat room : (20 million) | WIPO would have to set aside between 1.7 and 2.4 million francs (average cost: 2 million francs) for operating costs and the cost of external rentals. The cost of renting outside conference premises continues to be very high, as most of the meetings are attended by more than 400 participants (between 400 and 650). This option would therefore compel the Organization to continue to organize its conferences to a large extent outside, and, in the economist’s view would be an investment that made little or no sense. |
| --- | --- |
| 600-seat room : | Building a 600-seat conference room would call for an investment of 30 million francs, with the virtual certainty of having to organize future WIPO General Assemblies outside. |
| Room offering more than 600 seats: | The economist’s proposal is to build a room with a capacity in excess of 600 seats for a budget equivalent to the 30-million-franc project submitted. This option would correspond to WIPO’s aims and future needs, but it does entail a reduction in the average area per delegate. For an operating cost estimated at 2.25 million francs, in other words slightly above the average cost of a 400-seat room, it would thus be possible to accommodate future General Assemblies and the very large majority of other conferences that are organized. |

Consequently, and independently of the economic aspect, if WIPO nevertheless wishes to build a new conference room, consideration of the above options shows that it is preferable to build a room with a capacity in excess of 600 seats.  In spite of the Organization’s non-profit status, WIPO should be able to recover in any case part of the annual operating costs by renting its rooms to other organizations.  For the sake of reference, the WTO’s Salle William Rappard is rented for 7,000 francs a day (see paragraphs 52 and 54 for additional information).

What if any is the variation in the number of participants in WIPO meetings ?

- The number of conferences has remained stable since 1990.  On the other hand the number of participants has tripled in ten years.  Between 2000 and 2001 17 conferences (nine in 2000 and eight in 2001) were held outside, making a percentage of about 40% (eight of the conferences being for more than 250 people, including five for between 400 and 650).

- Major conferences for which participation is dependant on the number of Member States will see their attendance stabilize when the maximum number of 185 States is reached.  The maximum participation in the annual General Assembly should therefore flatten out in future at about 650 people.  Delegate participation in other types of meeting depends on the subject matter dealt with, and therefore cannot be forecast, so only conferences equivalent to the General Assemblies will serve to determine room capacity. 


What would be the ideal capacity for the conference room?

- The ideal number of seats for the conference room should at least make it possible to accommodate in the future, on the one hand, the WIPO Annual General Assembly in one place, and, on the other, the very great majority of the other conferences that are organized.

- Taking due account of the above factors, the construction of a 650-seat conference room offers the best balance between overall annual costs, and also a certain flexibility with respect to occupancy.  For events of the Diplomatic Conference type, where attendance exceeds 650 and the frequency of which is unknown, WIPO will have to organize linked meetings by connecting the new conference room to the present Room A, which would give a total capacity of 900 seats, or continue to rent premises outside.  In the latter case the cost of rental would have to be added.  That said, looking at the last ten years, one notes that a 650-seat capacity room would have accommodated the very great majority of WIPO conferences (only two would have had to take place outside).

| Scenarios | Room capacity (seats) | Investment in millions | Operating cost in millions | Rental cost in millions | Total in millions | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 4 | 650 | 30 | 2.25 | 0* | 2.25 | Increase in capacity from 600 to 650 seats, and reduction in the average area per place. |

*Calculated on the base of the last two years.  Meetings (over 650 seats unforeseeable) will have to be organized with a link (250+ 650 = 900 seats) or outside.  In the latter case rental costs would have to be added to the operating costs.

Should it be possible to divide the room?

- The additional cost represented by the installation of a partition is certainly considerable (1.5 to 2 million francs).  However such a partition is, in my opinion, necessary if the size of the room is to be adapted to the number of participants, if the chance of renting the rooms is to be improved (according to CICG figures, demand in Geneva is more for small rooms (100 to 200 seats)) and a growing need within WIPO for rooms of 100 to 250 seats is to be met.

It emerges from analysis of the conferences organized during the last ten years that they break down into three types:  those with 100 to 200 participants, 200 to 450 participants and 450 to 650 participants.  Division of the 650-seat room into two rooms of 450 and 200 seats would be the best way of meeting this need.

What amount would have to be invested ?

- At the present stage of the project (preliminary project for the conference room) it should be possible to increase slightly the capacity of the room, without increasing its cost, by adopting one or a combination of the following measures:

- Reduction in the average area per seat.  The ratio of net m2 per delegate provided with a desk ranges from 1.7 m2 for the Salle William Rappard to 2.0 m2 for WIPO room A and CICG Room No. 2.

- If one assumes that a minority of participants (about 30%) are considered “observers” and do not have a desk, one could reduce the average area per delegate.  For delegations of two persons or more (50% of delegations), it might be possible to arrange for some of them not to have a desk.  So a five-person delegation would have only three seats with desk, microphone and headset, while the other two seats would be immediately alongside but would have only headsets.  This arrangement, if ratified by WIPO, could make it possible to reduce the average area per participant (in this case from 2 m2 to 1.6 m2 per seat).

- By reducing the volume of the room.

Market survey

- A market survey on the infrastructural facilities in conference rooms that meet the needs of WIPO (600-seat or larger rooms) produced the following conference centers or hotels:  CICG, Palexpo, President Wilson Hotel, Salle William Rappard and UNOG.  As a general rule, owing to the small number of rooms available, room reservations for the above capacity in Geneva have to be made between 12 and 18 months in advance.  Events in Geneva take place generally during the same periods of the year, which adds to the problems of lack of infrastructure and complicates the reservation problem.  As for the cost of renting outside conference rooms, the hotels quote a rate almost double that quoted by the conference centers (see the economist’s reports for the details, reference 18).

1.4	VERIFICATION OF THE VARIOUS ESTIMATES

How was it that a budget of 82.5 million became an estimate of 180 million ?

- The 82.5 million budget seems to have emerged from earlier studies conducted by the K. Steiner company (former owner of the land), STG-Coopers&Lybrand and WIPO’s consultant architect.  They led WIPO to value the cost of constructing the main building on the basis of prices per m3 of 320 francs for the basements and 632 francs for the offices (indexed costs).  Analysis of similar buildings shows however that those figures were set too low (see table below), and WIPO’s use of them led to a serious underestimation of the budget.  Moreover, the volumes taken into consideration in the documents accompanying the budget are only theoretical, and do not allow for architectural solutions that might have cost implications.

- Table 8, Comparison of m3 SIA prices, with all CFCs combined (incl. fees)

- The net comparative area (net area allocated to the whole program, excluding the conference room and car park) is the only reliable element for comparison that can be used for all projects, and it has been noted that this net comparative area progressed from 13,889 m2 in Competition No. 1 in 1997 to 20,579 m2 in Competition No. 2 in 1999, representing an increase of  6,690 m2, and that without any account being taken of the increased area associated with the capacity of the conference room and the additional parking:

- Increase in working places from 450 to 500 (+ 2,527m2),

- Addition of a basement storage area (+ 3,000 m2),

- Addition of a library, staff welfare installations and various other facilities, representing a total of 1,163 m2.

- Thereafter that same area was increased further until the present figure of 26,897 m2 was reached in the final project, namely 6,318 m2 more than the figure for Competition No. 2 :

- Reduction in the number of offices (-2009 m2),

- Increased archive space (+ 1,'700 m2),

- Increased storage area (+4,485 m2).

- Increase in the surface allocated to various deposit areas, new area for shows, increased display areas and various other spaces, representing a total of 2,142 m2.

So, between 1997 (Competition No.1) and November 2001, we notice a 93% increase in the comparative area.

- As the volume specifications of Competition No.1 are not known, the SIA volume for WIPO’s 1997 estimate has been compared with the November 2001 final project.  There is a difference of 103,628 m3 between the two designs, corresponding to an 85% increase in volume.  By way of comparison, it is interesting to note that the 1997 estimate featured the three components of the complex (administrative building, conference room and additional parking).  The November 2001 final project likewise had three components, but with the difference of additional storage instead of additional parking.  On the other hand, the project of the competition winner does not incorporate the additional parking, and the conference room was integrated in the administrative building.

- Changes in SIA volume from 1995 to 2001

- As from Competition No. 2, which features a detailed specification with regard to the number and assigned purpose of premises, it is difficult to retrace the development of that specification.  There is no record of important decisions such as the shifting of the conference room or the reduction in the number of offices.  WIPO’s position regarding the development of the project and the proposal by the BB&P office is often non-existent and therefore hard to retrace in the literature made available to us.

- On the basis of an analysis of the various projects shortlisted in the last round by the judges of Competition No. 2 in 1999, it emerges that the BB&P project is in the lower part of the average with regard to both the areas and the overall constructed volume.  It should be noted that the constructed volume is not the same thing as the SIA volume, which adds to the latter a certain number of extras according to the account of the volumes.  Apart from that, as the choice was made by an international panel, I abided by their decision and therefore considered the architectural design to be a settled matter.

1.5  CONCLUSION

Requirements

- Evaluation of the November 2001 final project has shown that the needs with respect to working places would be fulfilled in so far as the scenario of an optimistic outcome establishes itself in the years to come.  In that eventuality, WIPO does however have to continue to rent the greater part of the P&G building.  Paradoxically, if the projections are more pessimistic, the P&G building is no longer rented and the specification is no longer met by the new administrative building with respect to either working places or parking places:  there is a working place shortage of 60 and a parking place shortage of 107 if one puts the parking place-employee percentage at 66%.  I think it is possible to remedy partly the 60 working place shortfall while respecting, on the whole, the intended architectural design.

- I note therefore that the reserve premises for the various staff evolution scenarios is outside the WIPO infrastructure, even as a new administrative building project is being planned.  Although the project under consideration makes use of the maximum capacities offered by the local district zoning plan, it does not allow all staff needs to be met (10% of those needs are not met in the pessimistic alternative).  On the other hand, the project submitted for analysis provides for greater representative areas.  A reassignment of those areas as working places in reserve would make it possible to achieve proportions that are more comparable with those of the buildings of other international organizations, and thereby to accommodate variations in staffing patterns better.  In that case the architectural concept might be affected.

- Table 6.6.  Representative areas in cross-section

Conference room

- As far as the conference room is concerned, surveys conducted have shown that the most economical alternative is not to build one.  However, experience has shown that profitability is seldom achieved with a conference room, which is why I consider that the argument for the construction of such a room has to be found more in a discussion focused on objectives and future needs and also on the convenience and independence that it affords.  So, if WIPO does after all want to build a new conference room, analysis of the alternatives shows that it is preferable to build a room with a capacity of 650 seats, which offers the best balance between overall annual costs and flexibility of use;  it seems wise to me, after all, to specify a conference room capacity that meets the requirements of the great majority of the expected meetings, like the Organization’s General Assembly.  If one adds the small difference in operating and rental costs between a 400-seat and a 650-seat conference room, and the fact that a 400-seat room does not make for a noticeable reduction in the cost of outside rentals, I would recommend the planning of a 650-seat room that is divisible into two rooms of 450 and 200 seats.  For events attended by more than 650 participants, WIPO could continue to rent outside premises or organize “linked” meetings.  This increase in capacity should be achieved without altering the 30-million-franc estimate for the conference room, either by reducing the average area per delegate place or by recognizing that some of the participants (about 30%) are to be considered “observers.”  These two proposals could also be combined.  Apart from that I have on a number of occasions pointed out that the planning of the conference room has not been completed, so a rationalization of the areas available would not strike me as being a problem at the present stage reached in the planning work.

- Costs and risks

Subject to the rebalancing and checking to be done on the costs written into the estimate, I can confirm that the amount of 180 million francs is a realistic package for the construction of an administrative building offering 500 working places (on average), a 280-place car park, a 650-seat conference room and additional storage areas.  However, the risks consecutive to the progress of certain parts of the project exceed the figures in the SIA standards by 6 million francs.  It is therefore necessary to bring about the completion of the planning of the conference room and technical installations as rapidly as possible in order to achieve maximum risk limitation.  I would also suggest to WIPO that it request the BB&P architect to submit an overall estimate that is accurate to +/- 5%, which corresponds to current standards on the Swiss market, in order to reduce the risk element still more (from + 24 million francs at present to + 9 million francs). The sum of about 16 million francs should be added to the estimate in order to cover WIPO fee costs (subject to the establishment of a project organization entity according to the proposal below), and also the project furniture and secondary expenses which would be higher than mentioned in the estimate.  Consequently the budget envelope for the November 2001 final project, given the additional costs mentioned (16 million francs), should come to :

196 million francs, accurate to +/- 10% according to the SIA standard, or 214 million francs if one considers the maximum allowable risk (+10%) according to the SIA standard, namely +18 million francs.

This figure does not allow for inflation, interim interest, contractors’ fees for possible updating of the final project according to WIPO decisions following the present evaluation, and removal expenses.  The over-valuation of the cost of additional storage space could turn out to be a substantial saving of about 6 million francs.  However, that reserve should be considered a buffer in the face of the considerable risks (+ 6 million francs) that are hampering the project.  Should the completion of the planning make it possible to lessen those risks, the sum in question could then be considered a saving.

Possible savings

- Considering the working facility that WIPO requires, I have mentioned the importance of rationalizing the project’s useful areas.  As my investigations failed to elicit any demonstrable need for additional storage space, other than the fact that it could be later converted into parking space, it seems to me that there is a potential saving of about 20 million francs in the option of not building that area.  There is no demonstrable justification for a delegate car park either.  In any case, the need for a 650-seat conference room takes precedence over the need for additional storage space.  This observation does not take account of possible synergies with the building of the new complex.  At the same time it would be advisable to consider rentals and the cost of implementing this option in parallel, in order to ascertain the relative advantages and drawbacks.

- As mentioned earlier, the budget envelope to be assumed for the construction of an administrative building, conference room and additional storage space would be 214 million francs.  Should the Member States act on my recommendation that no additional storage space be constructed, the envelope would then come down to 190.5 million francs.  Finally, if account is taken of the profitability of a conference room, the most suitable option would consist not only in abandoning the additional storage space but also in not building the conference room, whereupon the budget envelope would be about 158 million francs.  These figures assume a maximum permissible risk according to SIA standards of +10%.

- Given the different rates of progress on the phases of the project (pre-project and final project) depending on the buildings and contractors, it is difficult for me to submit accurate savings according to the type of work.  On the other hand, as a number of options and concepts have to be redefined or completed, I would suggest that they incorporate on the one hand, at the technical level, a spirit of modernity and respect for the environment as well as synergy with the existing installations, and on the other hand better use of usable areas (administrative building) and adaptation of relative volumes according to need (conference room).  The aim in implementing such measures would be not only to rationalize the project but also to achieve optimum use of the premises, in other words the working facility, which will ultimately, overall, result in savings.

- The necessity mentioned earlier of reworking certain headings in the November 2001 estimate means that potential savings (in heating, ventilation, air conditioning and excavation) would offset the cost increases noted (façades, plumbing and electrical installations, transport installations and climate control in the conference room).

- Other savings seem marginal in terms of the estimate (electricity supply, excessive acoustic demands made by the glazing of the outer fabric, overlaps between the sprinkler system and the fire hydrants).  It should also be mentioned that this building is no model of electricity consumption, as the large glazed areas lead one to expect the additional energy consumption for heating and air conditioning to be in excess  of 10 per cent when the building is operational.

Initial budget of 82.5 million francs

- The initial budget of 82.5 million francs was a serious underestimate, on the one hand because of the m3 price used, which was about 170 francs below what is customary for this kind of project, and on the other hand because the volumes used in the 1997 evaluation were only theoretical, and took no account of architectural solutions that might have an effect on costs.  Apart from that the areas and volumes have almost doubled between 1997 and the present project.

- At WIPO’s request I have made some recommendations regarding the action to be taken on the submission of this report, in response to its findings and to the decision of the Member States:  I wish to alert Member States to the fact that, before any call for tenders is issued for the implementation of the project, it is essential that the planning be brought up to date in the light of the report’s findings.  The final project must cover the specifications of the client totally and incorporate all its demands to the utmost degree of precision, in order to minimize as far as possible the risks of defects at the time of implementation, which could cause considerable additional expense:  experience has shown that every rider to a basic contract brings with it high costs that are often well in excess of market prices.  Apart from that, it strikes me as important to have a project management body as well as a representative of the client to carry out the coordination, management and verification that are essential to any project as extensive and as complex in terms of its execution as this one.  A body external to WIPO would be in a better position to respond effectively to the demands of the project and WIPO’s representative.

Summary of the response to the External Auditor’s terms of reference (see paragraph 2)

- For 2007, the Organization’s requirements amount to the following :

Working and parking places

| optimistic forecast : | 1,867 working places 1,020 parking places |
| --- | --- |
| pessimistic forecast : | 1,622 working places 1,174 parking places |

including the following for the new building :

| optimistic forecast : (the P&G building is still rented) | 427 working places 265 parking places (66% of staff) |
| --- | --- |
| pessimistic forecast: (the P&G building is no longer rented) | 612 working places 387 parking places (66% of staff) |

Storage areas :	3,000 m2

Additional parking for 
delegates and visitors :	280 places

Capacity of the new complex : 	554 working places,
		280 parking places,
		9,185 m2 of storage and archive space

Fulfilment of requirements in the new building :

| optimistic forecast : | The requirements are met if the P&G building is still rented |
| --- | --- |
| pessimistic forecast : | - 60 working places -107 parking places |
|  | + 6,185 m2 of storage and archive spaces |

Information technology should make it possible for the PCT to reduce by 126 a planned 866 working places in 2007 according to the optimistic forecast, making a corrected total of 740 working places.  At present the PCT has a staff of 490.

The profitability of a conference room of either 400 or 600 seats has not been established in our investigations.

The other possible solutions for technical installations are mentioned in Chapter 6 of Part II of this report.

The risk assessment points to additional costs of 6 million francs in relation to the state of the final project as of November 2001.  Those risks can be offset by the overvaluing of the cost of the additional storage space (by 6 million francs).  An amount of 16 million francs should be added to the 180 million francs of the confirmed November 2001 estimate for unforeseen expenses, which brings the overall budget envelope to 196 million francs at +/-10% (SIA standard).

- I should like finally to mention that the comments in this report have been formulated on the basis of not only the individual observations made by experts, but also their overall impressions, which impressions I share, being conscious at the same time of the complexity of such a project and the difficulties inherent in it.  The same complexity is to be found in the formulation of a specification reflecting the needs of the client, and its interpretation by the architect.  Apart from that, the physical distance separating the architect and the delegates clearly does not make for such an exchange of information as would enable the latter to form a better idea of the project.  Having said that, I invite all the delegates to become involved in this complex, ambitious and exciting project, so that they may fully understand its qualities and continue the work that started with the 1999 competition in order to create the working facility that WIPO needs.

K. Grüter

Director

FEDERAL AUDIT OFFICE

SWISS CONFEDERATION

(External Auditor)

## PART II

## Report and supporting arguments

2.	GENERAL

2.1	Terms of reference

- At their thirty-fourth series of meetings, held in Geneva from September 20 to 29, 2001, the General Assembly of the World Intellectual Property Organization (WIPO) and the Assemblies of the Paris, Berne, Madrid, The Hague, Nice, Lisbon, Locarno, IPC, PCT and Vienna Unions renewed the mandate of the Swiss Government as auditor of the accounts of WIPO and the Unions administered by WIPO, and also of the accounts of the technical assistance projects executed by the Organization up to and including 2003 (see paragraph 197 of document A/34/16).

- The Government of the Swiss Confederation mandated me, as Director of the Federal Audit Office, to audit the accounts of WIPO and of the Unions mentioned.  I entrusted a qualified colleague from the Federal Audit Office with the conduct of an audit, at the Organization’s International Bureau (IB) in Geneva, of the project to build the new WIPO administrative building.  This audit was carried out between November 2001 and June 2002.  In accordance with the recommendation of the Program and Budget Committee to the General Assembly held on September 17 to 20, 2001, the Swiss Federal Audit Office has called upon “other external experts (.....) for those areas which the external auditor judges not to be within his competence.”

- My terms of reference are stipulated in article 6.2 of the WIPO Financial Regulations, and defined by the “Terms of Reference Governing Audit” annexed thereto.

2.2	Subject of the audit

## See Summary, paragraph 2

2.3	Information and documentation

80.	I must express my thanks to all WIPO staff whom we approached for the obliging way in which they provided information and documents.

81.	In the course of their work, my colleagues frequently spoke with members of WIPO management and the representatives of regional groups and Member States attending the information meetings.

82.	WIPO organized five information meetings on the dates shown below.  These allowed the Swiss Federal Audit Office to give frequent updates on audit progress:

| November 27, 2001 | Presentation, to members of WIPO management, of the audit process and the options for the call for tenders |
| --- | --- |
| December 13, 2001 | Presentation, to members of WIPO management and representatives of regional groups, of the audit process and the planning of the procedure for the call for tenders |
| February 15, 2002 | Meeting to appoint the external experts, with a reminder of their terms of reference. Documentation relating to the terms of reference of all the advisers was also sent by electronic mail to representatives of Group B. Tables comparing the offers received and the audit program were given to representatives of the regional groups and to members of WIPO management at the meeting |
| February 22, 2002 | Presentation, to Group B Member States, of the structure of the audit process and the proposals for appointing external experts |
| April 26, 2002 | Intermediate information meeting on the progress of the various advisers’ analyses, attended by representatives of regional groups and members of WIPO management |

2.4	Development and structure of audit process

83.	At the first information meeting on November 27, 2001, my colleagues presented the audit process for evaluating the new building, as well as the options for the call for tenders for the external experts.  As a result it became apparent that the various analyses would have to be carried out by a group of technical experts as well as by an economist responsible for verifying the profitability of the conference room, with the work of the two groups being coordinated by the project manager.  With regard to time limits, the option of a restricted, invitation-only call for tenders was selected, as provided for in the WIPO Financial Regulations and Rules, allowing the report to be submitted on July 1, 2002 (see reference 1).  The open procedure provided for in law and in the rules governing public contracts would have shifted the time-scale back to September 2, 2002, which was not acceptable to WIPO.  The program presented to the representatives of the regional groups and to the members of WIPO at the meeting in Geneva on December 13, 2001, settled on the following time limits (see reference 2):

| Submission to WIPO of the list of contractors | January 14, 2002 |
| --- | --- |
| Timescales for submitting offers (outside experts) | February 8, 2002 |
| Meeting with representatives of regional groups and members of WIPO for appointment of experts | February 15, 2002 |
| Start of external experts’ audit | February 20, 2002 |
| Submission of advisers’ reports to external auditor | May 13, 2002 |
| Submission of final report by the Swiss Federal Audit Office | June 24, 2002 |
| Informal discussion within Program & Budget Committee | July 3, 2002 |

It should be noted here that all the above deadlines were met.

3.	APPOINTMENT OF GROUPS OF EXPERTS

3.1	Documentation submitted for study

84.	The first step for the various advisers in preparing their terms of reference was to collect and list the documentation relating to the project for construction of the new building since 1989.  This specific documentation was incorporated in all terms of reference during the tender process, then submitted to the advisers for them to begin their analysis (see reference 3).  This call for tenders was amended in the course of the analysis in the light of the requests and requirements of the experts (see reference 4) as well as the availability of information from within WIPO and from its contractors.  I also asked to be provided with an indication of projected staff requirements, taking account of the introduction of a computerized document management system called “IMPACT” (Information Management for the Patent Cooperation Treaty).  The IMPACT project should significantly rationalize and automate the workings of the PCT (Patent Cooperation Treaty), in particular ongoing tasks relating to data capture and the publication of applications, which will translate into a 20% reduction in staff needs for the same volume of applications.  Since a number of pilot modules have been in operation since the second half of 2001, it seemed important to me that the responsible members of WIPO should inform me of their initial observations in order to take them into account in my analysis.  Two reports prepared specifically by WIPO for evaluation of the new building were thus kindly made available to me.  The project review adviser and the economist studied these documents extensively.

  - Report 1, Needs for Office Space and Parking, April 11, 2002 (see Annex 1)

  - Report II, Needs for a Conference Room, March 4, 2002

A list of all the conferences organized by WIPO since 1990 was submitted to the economist at my request (see Annex 3).  The project review adviser later requested the head of the conference service to sort this list by conference type (see reference 5).  Finally, I shall mention the study of all the reports of the General Assembly and the Program & Budget Committee since 1989, which was carried out by the project review adviser and the economist.

3.2	Structure of the experts’ terms of reference

85.	The table below (diagram 1) summarizes the mandate given to me, and the resulting studies carried out in order to evaluate the project for the construction of a new administrative building with a car park, additional storage areas and a conference room for WIPO in Geneva.

Diagram 1

86.	There are four distinct areas of analysis:

(i) Verification of needs (chapters 4.4 to 4.6)

An inventory of needs, taken from various reports of the General Assembly and of the Program & Budget Committee since 1989, but also from pre-projects, competitions and estimates from 1993 right up to the present position in 2001, was carried out and compared with the specification of the actual “final project,” in order to determine whether the latter covers all WIPO’s present needs.  Account was also taken of the impact on the premises program of implementing a computerized document management system intended ultimately to rationalize staff needs.  This analysis was part of the project review adviser’s terms of reference, and allowed WIPO’s future needs to be evaluated.

87.	(ii) Current situation, evaluation of the “final project” (chapters 4.8 to 4.9)

An evaluation of the “final project” was carried out under the leadership of the project review adviser, with the cooperation of a multidisciplinary team including a civil engineering company, specialists in CVCS (heating, ventilation, air conditioning and plumbing), electrical engineers, a building physicist and a sound engineer.  The project review adviser coordinated the management of the various technical specialists’ studies (diagram 2).  I asked the various experts to structure their analysis in line with two principles: the first purely functional, the second architectural or formal.  The project does indeed have two aspects: on the one hand a functional volume requirement linked directly to the client’s needs and, on the other, representative areas which are defined by the specification and the architectural language chosen by the competition winner.  Particular attention was also paid to an appreciation of the structural and technical aspects of the project, the opportunities for flexible use and extension of different areas, maintenance and, of course, control of costs.

88.	(iii) Evaluation of the profitability of a conference room (chapter 4.10)

Assessment of the profitability of a conference room (diagram 1) was carried out in parallel by an economist setting up the second study group (diagram 2).  As a complement to this study, the project review adviser was also asked to look into future needs.

89.	(iv) Verification of the various estimates (chapter 4.7)

Finally, the project review adviser reviewed the various estimates by comparing them with their respective projects (diagram 1).

90.	The project manager directed this process and coordinated the two study groups.  He collated the reports of both groups and drafted the final report (diagram 2).

(Diagram 2)

3.3	Call for tenders

91.	The call for tenders for external experts took place between January 18, 2002 and February 8, 2002, as set out in the program. Twenty-two experts responded to the 26 invitations to tender sent.  My colleague selected and interviewed 11 companies, and finally proposed the eight experts listed below to representatives of the regional groups and members of WIPO management at the meeting to appoint the experts on February 15, 2002.  This choice was accepted without modification (see references 6 and 7).

| Project Review | Tekhne Management SA Mr Baeni, Mr Braune Avenue de la Gare 33, 1000 Lausanne |
| --- | --- |
| Civil Engineer | Fellrath & Bosso SA Mr Bosso Chemin de Maillefer 37, 1052 Le Mont-sur-Lausanne |
| Heating, Ventilation and Air Conditioning Engineer | Sigma Ing. Conseil SA Mr Coutaz Avenue de la Gare 10, 1003 Lausanne |
| Plumbing Engineer | Sigma Ing. Conseil SA Mr Coutaz Avenue de la Gare 10, 1003 Lausanne |
| Electrical Engineer | Bering AG Mr Hofer Papiermühlestrasse 4, 3025 Berne |
| Building Physicist | Leuthe & Zimmermann Mr Leuthe Ruelle du Haut 4, 2500 Bienne 3 |
| Sound Engineer | AAB J.Stryjenski et H. Monti SA Mr Monti Rue des Noirettes 32, 1227 Genève |
| Economist | Horwath Consulting Mr Birr Rue du Jeu-de-l’Arc 15, 1211 Genève 6 |

3.4	Budget Envelope

92.	At the meeting on February 15, 2002, my colleague presented tables comparing the tenders received from the various advisers.  The overall budget envelope for evaluating the new building with the advisers was estimated at 440,000 francs.  Two complementary studies relating to the acoustics of the administrative buildings and to the verification of future requirements for the conference room were requested and posted to the reserve fund included in the above sum.  At the time of writing, the detailed breakdown of the costs of this evaluation has not been finalized.

3.5	Analysis Program

93.	An analysis program was defined and submitted to the various advisers at the first working meeting on February 20, 2002.  This program sets out a framework for the studies in five phases with six coordination meetings (see reference 8):

| Phase 1 | Verification of documents and study of documentation submitted | February 20 to March 8, 2002 |
| --- | --- | --- |
| Phase 2 | Functional and Architectural Analysis | March 8 to 21, 2002 |
| Phase 3 | Analysis of Costs | March 21 to April 11, 2002 |
| Phase 4 | Synergies | April 11 to 25, 2002 |
| Phase 5 | Drafting of report Report submission | April 25 to May 8, 2002 May 13, 2002 |

4.	ANALYSIS

4.1	Definition of framework of analysis (see reference 9)

Only the architect has reached the final project stage.  As for the conference room, it is still at the pre-project stage.

Certain elements critical to the studies, such as the car park, are not yet complete.

94.	The study refers to the November 2001 final project and estimate.

95.	The documentation supplied to the various advisers at the start of their analysis caused them to question the exact status of the project phases.  In fact, the documents from the civil engineer and building facilities engineer fell far short of what one might fairly expect from a final project.  In order to define clearly the framework of our analysis, I had a table drawn up summarizing the contractors’ contributions as at November 29, 2001, which was the date on which the estimate for the construction of the final project was submitted to WIPO.

96.	The contributions of the architect as of November 29, 2001, fully cover the pre-project phase, with about 2% of the project phase remaining before the overall estimate can be finalized.

97.	As the overall estimate was presented to WIPO on March 28, 2002, a month after the experts began their work, it was not included in their studies.  They therefore focused on the estimate of November 29, 2001.  This estimate, which according to the architects (BB&P) was accurate to +/-10%, was calculated on the basis of reference prices, not on a specification.  It became clear that no proper comparison could be made between the estimate of November 2001 and the overall estimate of 2002, given that the project had evolved in the meantime.

98.	Although the label of “final project” is broadly valid for the architect’s contributions, the same cannot be said for the civil engineers and the special installations engineers: 40% of the work has still to be done by the civil engineer to reach the final project stage, and about 50% in the case of the electrical and CVCS engineers.

99.	Moreover, even though the architect’s final project document is almost complete, it is clear from perusal of the plans that the study of the conference room is at the pre-project stage at best.  Also, some important elements of the project, such as the mezzanine, the study of the load-bearing structure and the car park, are not complete.  More detailed study of this last part of the work could have a significant impact on the upper floors and on coordination.  This will doubtless have financial repercussions (fees) and cause a planning delay.

100.	Coordination between the various members of the planning team (in particular between those responsible for air conditioning, ventilation, plumbing and electrical installations) does not appear to be adequate, a fact made clear by the information brought to our notice.

101.	It is a fact that the accuracy of estimates is closely linked to the state of progress of the study.  Given that the architect and his technical contractors are at different stages, it is reasonable to suppose that the accuracy of the estimates is between –5% and +10% for the architect, and between –10% and +20% for the others.  The degree of accuracy of the estimates is illustrated in table 7 of paragraph 248 and in paragraph 249.

4.2	Mission

102.	The areas of analysis, as described in chapter 3.2, were summarized by the project review adviser in the form of five questions (see his report, reference 10).  His studies are set out in chapters 4.3 to 4.9.  The observations of the project review adviser are complemented by the studies of the other advisers in chapter 4.8, relating to the analysis of the final project.  Finally, chapter 4.10 analyses the findings of the economist and the project review adviser on the profitability of the conference room and adds six further questions concerning the room in addition to those shown below.

(i) Verification of needs

- What are the current terms of reference?

- How did the specification evolve over time?

(ii) Evaluation of the final project

- Does the future building meet WIPO’s needs?

- Are the planned costs reliable?

(iii) Assessment of the profitability of a conference room:

- Is a conference room profitable at all?

- What is the variability of the number of participants in WIPO meetings?

- What number of seats meets WIPO’s current and future needs?

- What would be the ideal capacity for the conference room?

- Should it be possible to divide the room?

- What amount would have to be invested?

(iv) Verification of the various estimates:

- How was it that a budget of 82.5 million became an estimate of 180 million?

4.3	Context and WIPO Objectives

The role and importance of WIPO continue to grow

103.	WIPO observes that the current trend is towards an increased role for intellectual property in a number of areas, including the economic, the cultural and the social.  WIPO believes that this trend will continue and even increase over the next ten years.

104.	This trend, as one would expect, is accompanied by a considerable increase in applications for patent registration.  Although not in proportion to this increase, WIPO staffing levels have grown markedly in recent years, rising from 650 in 1995 to almost 1300 at the end of 2001.  Latest forecasts of staff numbers show an acceleration of this growth, despite the introduction of computerized methods.

The Organization wishes to open up more to the public

105.	Moreover, WIPO has resolved to demystify intellectual property rights through a campaign of awareness and communication aimed at making the intellectual property system and the Organization more accessible to the public (in line with the objectives set out in WIPO’s “Future Vision” document).  The planned new complex must also be part of this openness campaign.

The new building must symbolize WIPO and should be modern, functional and economic

106.	Based on various official documents, the overall objectives set by WIPO for its new building can be summarized as follows:

The World Intellectual Property Organization (WIPO) wishes to create on a single site a coherent architectural complex that meets the operational needs of the Organization and responds to the constant development of its activities.  The objective of the competition is not to construct a building alongside the current headquarters, but to create the urban image of a unique architectural space that symbolizes WIPO.

107.	Extract from the rules of Competition No. 1: WIPO plans to create a complex of buildings of high architectural quality that will facilitate its activities and make use of 21st century technology.  The projects must take account of the objectives of the organizer, namely the creation of a complex of buildings with the following characteristics:

- Technical intelligence

- Respect for the environment

- Functionality, convenience, economic rationality, energy efficiency, technological efficiency

- A pleasant environment for workers and visitors

108.	Extract from the rules of Competition No. 2:

Moreover, in a reference document relating to the construction of the new building (WO/GA/23/5 of July 29, 1998), WIPO describes its objectives as follows: The new office building will therefore need to provide at least 500 working places, and must be a functional, utilitarian, modern and fully operational building designed to answer the precise needs and functional requirements of the Secretariat while, at the same time, offering maximum flexibility so that the modular working places could be re-arranged to enable future needs to be accommodated.  This building will incorporate the latest information technology facilities, including high bandwidth cabling throughout the building and video-conference and other electronic conference facilities, so that staff can make maximum use of information technology in their work, thereby enabling them to work in the most efficient and productive manner;  this is particularly important in the context of WIPO’s computerization and information technology oriented projects. Through the effective use of information technology and new ways of using space, the building should allow for the possibility of accommodating larger numbers of staff in the future.  The building can therefore be characterized as being an “intelligent” and operational building (the building should also be “intelligent” in incorporating the latest building technologies, to be environmentally adaptable and energy-efficient).

109.	Summary of the judgement of the competition: The successful project is the one that most clearly reflects WIPO’s future vision.  It is modern and respects the most important ecological aspects – it is a project for a new generation.  The building is neatly integrated in the site, in that it takes advantage of the existing landscape and brings the outside world into the building.  The open space devoted to offices is the most flexible of all the elements and it will be a pleasure to see it unfold.  The ground floor gives an impression of movement and fluidity, thanks to the way the various areas are combined, and its general configuration emphasizes the importance of the location.

  - Changes in needs and buildings inventory

    - Changes in needs between 1993 and 2001

Needs expressed in terms of working places depend on the available buildings

110.	The need for working places on the “Steiner lot” has always been closely linked to the planning of this development and to the buildings at WIPO’s disposal (whether owned or rented).  (See table 2 in reference 10 “Inventory of buildings used by WIPO as of April 11, 2002”).  In fact, in order to know what the specification of the new building was at any given date, one would also need to know what buildings were available to WIPO at that time.

	WIPO acquired or rented various additional buildings between 1993 and 2001.  WIPO’s February 2002 forecast of a need for another 500 working places remains valid in view of the increase in staff numbers.

111.	From 1993 to the present day, the following salient facts need to be considered:

- In 1993, WIPO decided to buy the WMO building and to convert it (450 additional working places from 2003),

- In 1995, WIPO decided to enlarge the BIRPI building (120 additional working places),

- In 1995, WIPO decided to rent the whole of the Procter & Gamble building apart from one floor (430 additional working places)

112.	These factors demonstrate that it is not possible to compare the 1993 specification with that of 2002, since the available buildings had changed considerably.  On the basis of various forecasts done by WIPO at regular intervals, we can see the following changes:

Summary of forecast staffing levels for the years 2005 to 2007:

| Date of Forecast: | 2005 | 2006 | 2007 |
| --- | --- | --- | --- |
| August 1994 | 1152 |  |  |
| March 1996 | 1215 | 1275 |  |
| July 1996 (Sugden) |  | 1300 |  |
| February 1997 (STG) | 1215 | 1300 |  |
| February 1998 | 1238 | 1300 | 1361 |
| September 2000 | 1565 | 1643 | 1725 |
| April 2002 |  |  | 1778 |

Sources: WIPO documents

Note: the figures mentioned do not include a reserve of 5% normally required according to WIPO

in order to assign working places correctly

113.	Thus between 1994 and 2000, the staffing forecasts for 2005 increased by 36% (from 1,152 to 1,565), for 2006 by 29% (from 1,275 to 1,643) and for 2007 by 31% (from 1,361 to 1,778).  Forecasts done since 2000 show a considerable increase in staffing levels for the year 2007, despite the introduction of new computer resources.

    - Buildings inventory (see reference 10, table 2)

114.	The inventory of buildings used by WIPO was based on information contained in report 1 of April 11, 2002 (Report 1, Needs for Office Space and Parking, April 11, 2002), as well as on various information contained in minutes of the Premises Committee.  Today WIPO has 1,589 working places available, to which 450 places under construction in the former WMO building will be added in 2003, making a total of 2,039 spaces, including 1,010 (50%) owned by WIPO.  In addition, there are currently 1,028 parking places, plus 180 currently under construction, making a total of 1,208 available places, including 419 (30%) owned by WIPO.

4.5	Latest Staffing Forecasts

The latest available staffing forecasts are contained in report 1 of April 11, 2002 (Report 1, Needs for Office Space and Parking, April 11, 2002).

Despite the introduction of the IMPACT system, the rise in staff numbers seems inexorable: they have gone up again in the latest forecast.

In summary, the latest WIPO forecasts are based on the factors listed below:

115.	WIPO observes that the current trend is towards an increased role for intellectual property in various areas, particularly economic, cultural and social.  WIPO believes that this trend will continue and even increase over the next ten years. The number of parties to the various WIPO treaties has increased considerably.

116.	The PCT system is growing rapidly: the number of applications increased by 16% per annum between January 1996 and December 2001.  The “optimistic” growth in staff numbers, which is not in proportion to the growth in applications, takes into account an annual factor of 11.5% in 2002, declining to 7.9% in 2007.  This “optimistic” forecast implies an increase in PCT staff from 490 today to 866 in 2007.

117.	The IMPACT program should allow a saving of 23% in staff numbers following its introduction, according to a study by Deloitte and Touche in 1998.  This corresponds to a reduction of 126 places in 2007 (“optimistic” growth), or a corrected total of 740 PCT places.

118.	Madrid system: this system has a good chance of being extended to other geographical areas.  Indeed the accession of the United States to this treaty could create “major unplanned growth” in the near future.  This growth could double the number of international registrations filed.

119.	Forecasts of the number of employees for the Madrid and The Hague systems are based on growth rates ranging from 3.2% (pessimistic) to between 4.3% and 12.8% (optimistic), equating to staff numbers of between 114 and 146, compared with the current figure of 90.

120.	In addition to the office needs for WIPO employees, the WIPO buildings must also accommodate external services (e.g. travel agency, restaurant management, security guards and other WIPO sub-contractors), as well as employees of UPOV.

121.	Another factor to be borne in mind is that WIPO believes that a sensible allocation of working places requires a reserve to be added of 5% of the total number of places.

122.	Table 3 in reference 10 summarizes the staff forecasts for the year 2007.  Although these forecasts are hard to verify in the light of the ever-changing IT situation, it seems to us that the bases of calculation can be considered reasonable, even in the optimistic forecasts.

123.	The growth rates are in fact cautious, even in the “optimistic” forecast, and do not take account of the difficulties inherent in the introduction of new computer systems, or of the likelihood of paper-based and IT systems existing side by side for an unknown length of time.

4.6	Present terms of reference

In the light of the latest WIPO forecast, the terms of reference for the year 2007 may be summarized as follows:

4.6.1	Staff

124.	A staff strength of 1,778 is planned for 2007, which corresponds to a requirement of 1,866 working places, taking account of the need for a 5% reserve.  If only the buildings owned by WIPO are included, the needs of the Organization in 2007 can be summarized as follows:

|  | Optimistic Forecast | Pessimistic Forecast |
| --- | --- | --- |
| Forecast staff level (including reserve): | 1867 | 1622 |
| Spaces available in WIPO-owned buildings: | 1010 | 1010 |
| Working places required: | 857 | 612 |

125.	In the optimistic forecast, the new building will not meet this requirement.  However, by continuing to rent the greater part of the P&G building, the number of working places needed in the new building will be:

|  | Optmistic Forecast | Pessimistic Forecast |
| --- | --- | --- |
| Working places required: | 857 | 612 |
| Spaces rented from Procter & Gamble: | 430 | 0 |
| Working places required: | 427 | 612 |

126.	The pessimistic forecast presupposes WIPO discontinuing rental of the Procter & Gamble building and accommodating all staff on its own premises after the construction of the new administrative building.  The need for working places is therefore between 427 and 612, which corresponds to an average demand for 500 working places.

4.6.2	Parking places

127.	WIPO estimates that 80% of its employees require a parking place.  Once the renovation of the former WMO building is complete, WIPO will have in its own buildings 395 basement places and 24 outside places for visitors.

128.	On the basis of the staffing forecasts for 2007, the requirement for parking places can be estimated as follows:

|  | Optimistic Forecast | Pessimistic Forecast |
| --- | --- | --- |
| Parking places required (staff numbers without reserve x 80%): | 1,422 | 1,236 |
| Spaces available in WIPO-owned buildings: | 395 | 395 |
| Parking places required: | 1,027 | 841 |

129.	Taking account of space rented in the Procter & Gamble building, immediately adjacent to WIPO, the number of parking places required in the new building can be justified as follows:

|  | Optimistic Forecast | Pessimistic Forecast |
| --- | --- | --- |
| Parking places required: | 1,027 | 841 |
| Spaces rented from Procter & Gamble: | 275 | 0 |
| Parking places required: | 752 | 841 |

130.	Taking account of spaces currently rented in the Parking des Nations, immediately adjacent to the site, the need would be:

|  | Optimistic Forecast | Pessimistic Forecast |
| --- | --- | --- |
| Parking places required: | 752 | 841 |
| Spaces rented in the Parking des Nations: | 238 | 238 |
| Parking places required: | 514 | 603 |

Note: These figures do not take account of the periods when delegates are in Geneva.

131.	The requirement for parking places in the new building can therefore be estimated at between 514 and 603 places.  However, the ratio of 80 parking places per 100 employees seems extremely high for an urban site, in an area well served by public transport, 15 minutes’ walk from the station.  Also, the imminent opening (in 2003?) of tram route No. 13 will improve the situation still further.  By way of comparison, the new WMO building has 410 parking places for 625 daily working places and 250 temporary working places during conferences, which corresponds to 66% of the working places.  At a rate of 66%, the requirement would be for 265 places in the optimistic forecast, and 387 places in the pessimistic forecast (in which the Procter & Gamble building is not rented), which seems more realistic.

4.6.3	Storage space requirement

132.	This element of the program is difficult to quantify.  Document WO/GA/23/5 of July 29, 1998 speaks of an extension of the present WIPO car park that would allow 280 places to be added for delegates and visitors at conference times.  This car park, although mentioned in the introduction to Competition No. 2, is not described in terms of area and capacity.  What is more, it does not appear in the winning design.  However, these areas are found in the final project, but their intended use is put as storage, whereas the need for this type of area is not specified anywhere.  We infer from this that the storage area could one day be converted into a car park, thereby acceding to the requests of Member States.  Apart from this large area, storage needs are defined in the rules of Competition No. 2.

133.	Parking places for delegates

When they are present in Geneva, delegates attending WIPO conferences use other forms of transport (city buses, shuttle buses, taxis) rather than private cars.  The need to provide a dedicated car park for this category of temporary visitors has yet to be proved, and would require examination in greater depth.

4.7	Evolution of the projects

    - History

After a detailed study of the various projects, it must be said that they are not all comparable, owing to the lack of information relating to some of them.  However, the following chronology can be established:

134.	1989

One of the first preparatory meetings on the construction of new premises put forward a cost of 1,000 francs per m3 and a volume to be built of 130,000 m3, making an investment of 130 million francs.

The net comparative area changed from 16,184 m2 in the Steiner project of 1995 to 26,897 m2 in the November 2001 final project.

135.	1995

The Steiner project was costed at 96 million francs in its full version, i.e. with linking footbridge and a fourth basement level.  Its net comparative area was 16,184 m2.  Advanced contacts took place between WIPO and the Steiner company with a view to carrying out this project as a joint enterprise.

136.	1997

STG/Coopers-Lybrand estimated however that the cost of this work was too high and reduced it in its calculations from 764 francs per m3 to 550 francs per m3.  WIPO’s consultant architect assessed at that time the possibility of creating a new conference room close to the existing one.  The budget was estimated at 12.5 million francs.  He also assessed the possibility of doubling the capacity of the existing basement car park for delegates.  The budget for this 290-place garage was estimated at 7.9 million francs.

The budget of 82.5 million francs was underestimated, as a result of conflicting information from different studies.

137.	1997

It appears that WIPO worked out a budget of 82.5 million francs on the basis of different information calculated by Steiner, STG and its consulting architect, broken down as follows:

| International architectural competition | 1.5 million |
| --- | --- |
| Establishment of detailed specification | 2 million |
| Construction and connecting up of new building | 46 to 51 million |
| Furniture and equipment for the new building | 5 million |
| Construction of the new main conference room | 12 to 15 million |
| Construction of additional car park | 8 million |
|  | 74.5 to 82.5 million |

138.	1997

The first exhaustive specification was worked out in 1997 with a view to launching an architectural competition.  The net comparative area was then 13,889 m2.  This competition was subsequently abandoned.

139.	1998

WIPO purchases the Steiner lot.

140.	1998

A second specification was drawn up with a view to launching a second competition.  The net comparative area was now 20,579m2, or 6,690 m2 more (see table in paragraph 151) than in Competition No. 1 (without taking account of the increase in area caused by the increase in the conference room to 600 seats and the additional car park).  The contestants’ plans had to comprise three parts: an office building, a 600-seat conference room and an extension of the basement levels of the current headquarters (delegates’ car park).

141.	2000

In March, the independent panel awarded first prize to BB&P.  The successful project had a net comparative area of 22,431m2 and was below average for the projects presented, both in terms of gross floor area and built volume.  It should be noted that at this stage the project planned to incorporate the conference room in the overall building.  Also, the winner did not mention the third element of the program, which was the car park for delegates (which doubles the size of the existing building’s car park).

142.	2001

In August, BB&P drew up a pre-project in which the conference room was removed.  This project included a separate room as well as a delegates’ car park that had become an “independent storage area.”  The net comparative area was now 29,004m2.  In November, BB&P submitted its final project, which forms the basis of the document submitted for our scrutiny.  The net comparative area was now 26,897m2, or 6,318 m2 more than in Competition No. 2 (see table in paragraph 152).

4.7.2	Net comparative area of the various projects

Note: Net comparative area means the net area allocated to the whole of the program, excluding the conference room and the car park. This area is the only reliable comparator that can be identified in all the projects.

143.	Table of net comparative area for each project:

|  | Net m2 (exc. conference room and car park) | % | Net m2 (inc. conference room and car park) |
| --- | --- | --- | --- |
| Steiner Project version C (1995) | 16,184 | 100 | 23,034 |
| WIPO estimate (1997) | Not available |  | Not available |
| Competition No. 1 (1997) | 13,889 | 86 | Not available |
| Competition No. 2 (1999) | 20,579 | 127 | Not available |
| BB&P winning project (2000) | 22,431 | 139 | 34,841 |
| BB&P pre-project (2001) | 29,004 | 179 | 34,929 |
| Current project (11/2001) | 26,897 | 166 | 32,581 |

4.7.3	SIA volume of the various projects

144.	Table of SIA volumes for each project:

|  | SIA m3 complete project | % |  |
| --- | --- | --- | --- |
| Steiner Project version C (1995) | 135,487 | 100 |  |
| WIPO estimate (1997) | 122,650 | 91 |  |
| Competition No. 1 (1997) | Not available |  |  |
| Competition No. 2 (1999) | Not available |  |  |
| BB&P winning project (2000) | 166,400 | 123 |  |
| BB&P pre-project (2001) | 231,368 | 171 |  |
| Current project (11/2001) | 226,278 | 167 |  |

The table above allows a comparison between the various projects for the new plot, highlighting a difference between the volume in the WIPO estimate of 1997 and the final project in 2001 of +103,628m2.

4.7.4	Changes to the specification since 1997

145.	Comparison of projects selected in the 1999 Competition:

Analysis of the various projects shortlisted in the final round by the panel in Competition No. 2 shows that the BB&P project is below average in terms of built area (BA), gross floor area (GFA) and built volume (BV). It should be noted that the BV  is not the same thing as the SIA volume, which adds to it a certain number of extras according to the account of the volumes.

146.	1997 specification (Competition No.1):

It was specified that the building should offer at least 450 working places, representing 924 modules of 135cm x 550 cm, a 400-seat conference room divisible into two rooms of approximately 250 and 150 seats respectively, and three meeting rooms of 40 seats each for consultation and meeting preparation.

147.	Specification drawn up by STG Coopers & Lybrand (February 1997):

This report provided some interesting pointers on the ratio of net/gross area per employee.  It also added to the 1996 Sugden report by allocating areas to Mr Sugden’s staffing forecasts. This report also contained a sheet relating to the building project on the Steiner lot, which mentioned a sale price of 77 million francs, whereas STG estimated the project value at no more than 55 million francs. It seems that this corrected figure was one of the factors that influenced WIPO in its financial estimates for the future building.

148.	1999 specification (Competition No. 2)

The Competition stipulated that “the complex of buildings shall comprise”:

- an office building

- a conference room with annexes (…)

- extension and remodelling of the lower floors of the main WIPO building (…)

149.	It was desired that the new conference room be located in the immediate vicinity of thepresent ones, but in fact that was left to the discretion of the contestants. Even so, it is reasonable to assume that since the contestants had to respect the local district plan (PLQ), which did not provide space for a separate room, they integrated this room in the main building.

150.	Moreover, the introductory paragraph of this document left room for an additional car park program that is not explicitly stated anywhere in the rules.

4.7.5	Changes to the program between the Competitions and the November 2001 final project

151.	Differences between Competition No. 2 and Competition No. 1:

| Program | Net area (m2) | Comments |
| --- | --- | --- |
| Increase in the number of working places from 450 to 500 and increase in the average area per working place (A) | 2,527 | 1,285 modules instead of 924, i.e. 361 extra modules of 7m2. The increase in area is greater than the increase in working places |
| Capacity of conference room increased from 400 to 600 seats (B01) | (350) | WO/GA/23/5 (para.23). Estimated additional area not added |
| Addition of one extra press room | 30 |  |
| Increase in the size of the preparation area (B.10) | 20 |  |
| Increase in the size of the cloakrooms (B.11) | 20 |  |
| PC area for delegates (B.13) | 150 |  |
| Secretariat for conference rooms (B.14) | 77 |  |
| Reduction in size of reception area (C.02) | -30 |  |
| Addition of an exhibition area (C.07) | 100 |  |
| Addition of a library and reading room (C12) | 500 |  |
| Increase in kitchen staff cloakroom (E.17) | 15 |  |
| Addition of basement storage areas (E.17) | 3,000 |  |
| Addition of staff welfare facilities (E31) | 400 |  |
| Motorcycle places |  | 100 places |
| Bicycle places |  | 100 places |
| Addition of extra car park for delegates (280 spaces) |  | WO/GA/23/5 (§35) |
| Various fluctuations | -119 |  |
| TOTAL NET ADDITIONAL M2 | 6,690 | Not including additional car park and motorcycle and bicycle places |

Numbers refer to the program of Competition No. 1

152.	Differences between the “final project” program and Competition No. 2:

| Program | Net area (m2) | Comments |
| --- | --- | --- |
| Reduction in number of offices (A) | -2,009 | 998 modules instead of 1,285 specified, i.e. 287 fewer modules of 7m2. |
| Removal of one meeting room adjoining the main room | -60 |  |
| Addition of a separate kitchen for the main room | 160 | Due to the new positioning of the main room |
| New computer area | 165 |  |
| New registration area | 30 |  |
| New Chairman’s cloakroom | 65 |  |
| Reduction in size of entrance room | -150 |  |
| Removal of security staff area | -25 |  |
| Increase in exhibition areas (C.07) | 250 |  |
| New show area | 270 |  |
| Infirmary converted to medical center (C.10) | 180 |  |
| Increase in area allocated to various storage facilities | 613 |  |
| Increase in archive areas (E.27) | 1,700 |  |
| Increase in storage areas (E.30) | 4,485 |  |
| Various fluctuations due to normal evolution of the project | 644 |  |
| TOTAL NET ADDITIONAL M2 | 6,318 |  |

Numbers refer to the program of Competition No. 2

4.8	Analysis of the November 2001 final project

4.8.1	Project review

153.	Principal characteristics of BB&P’s final project, November 2001:

| Net comparative area: | 26,897 m2 |
| --- | --- |
| Total net area: | 32,581 m2 |
| Gross floor area (GFA): | 51,355 m2 |
| SIA volume: | 226,278 m2 |
| Number of working places: | 429 to 569 |
| Number of parking places: | 13 places for suppliers 280 places for staff |
| Restaurant: | 300 seats |
| Cafeteria: | 300 seats |
| Conference room: - Divisible into: | 600 seats 280 seats/320 seats |

The net comparative area increased from 20,579 m2 in the Competition specification to 26,897 m2 in November 2001.  At the same time, net office space fell from 9,560m2 in the Competition specification to 7,749m2 in November 2001.

The number of office modules has thus been reduced from 1,285 at the time of the Competition to 998 in November 2001.  This elimination of 285 modules corresponds to a potential shortfall of about 140 offices at 14m2.

Examination of the plans gives rise to the following observations:

154.	From the time of the Competition, the BB&P project stood out because of the decision to integrate the exterior and interior of the building.  This is achieved particularly by the “free” ground floor, which simulates hills and a forest (of pillars). This volume occupies two floors containing the “representative” areas of the building.

155.	On an unspecified date in 2001, at WIPO’s request, the conference room was removed from the main volume calculation to become an independent feature located close to the present headquarters.  Petitions made by WIPO (represented by their consultant architect) to the authorities made this situation possible, although at the time of the Competition it was still uncertain.  It should be noted that the volume of the new building without the conference room remained the same.

156.	The present architectural project achieves WIPO’s expressed objective of opening up the organization, as summarized in the introduction to this document.

157.	Architecturally, the new building is divided vertically into three distinct units:

- the car park with its own building structure

- the “free” ground floor

- the “conventional” office floors

158.	Despite this apparent simplicity, the superposition of these different albeit traditional activities creates structural constraints that make little sense.  Owing to the stairwells and lifts on the upper floors, the car park does not have an optimum layout and has a very large area for each parking place (38m2 per place, rather than the normal 25m2).

159.	The spiral configuration within the car park and the design of the access ramp make circulation of vehicles at peak times difficult.

160.	The entirely open areas on the ground floor raise various questions regarding the ambient climate (large open areas allow odours, noises and draughts to circulate on the office floors).  Resolving these issues could have significant financial implications (see the report of the sound engineer on this topic, reference 17).

161.	Currently, data relating to the mezzanine are partially incomplete and do not allow costs to be verified.

162.	The design of the ground and mezzanine floor areas derives from the architectural concept of “outside spaces.”  Following the removal of the conference room, these areas seem out of proportion to their actual use, even for what are called representative areas.  This substantially increases the ratio of area (and volume) per working place, and upsets the economics of the project.

163.	The number of modules at 7m2 allotted to offices went from 1,285 units in the specification of Competition No. 2 to approximately 998 now, i.e. a potential reduction of 140 working places.  The office floors are laid out in individual offices, but with a few adjustments, it would be possible to add some group offices.  Apart from the possible reassignment of some relaxation areas as offices (approximately 30 working places), the project does not have any other areas in reserve.

164.	The stairwells and the service areas are arranged at the front of the building, which gives a more vibrant appearance but also takes away areas that are ideal for working places.

165.	The security zones requested by WIPO are not completely identifiable and seem to conflict with the “dispersed” layout of the lifts and stairwells.

166.	The load-bearing structure of the offices reveals several offset elements in the framework, which seem to owe more to architectural concepts than functional necessity.

167.	The conference room also gives the impression of having more to do with architectural concepts than the specification.  By way of proof, the division of the room does not correspond to the original request and visibility is not ideal for some participants and for the translators.

168.	The third element of the program has been converted from a car park to an independent storage area, although to date no document has indicated to us why this should be necessary.

169.	On analyzing the overall project, one notes that what are called the “secondary volumes” (car parks, storage areas, etc.) have become greater than the volumes set aside for “primary” needs (offices, conference room), although the latter were the original reason for which the building was to be constructed.  The volumes devoted to the representative areas (restaurant, mezzanine, reception areas) should be stressed.  The tables below illustrate this observation.

170.	Table 6. Allocation of SIA volume

171.	Table 6 bis. Allocation of gross floor area

4.8.1.1 Fulfilment of the specification

The present status of the final project suggests that WIPO’s needs will be met in the optimistic version, with the P&G building continuing to be rented.  In the case of the pessimistic version, which should allow needs to be met without having to rent the P&G building, needs will not be covered by the new building.

172.	Working places

As mentioned above, the number of working places in the new complex by 2007 will be between 427 (optimistic version) and 612 (pessimistic version).  In the optimistic scenario, WIPO would have to continue to rent the P&G building, while in the pessimistic  scenario, it is feasible to accommodate the entire staff of WIPO in its own buildings.

173.	Analysis of the plans of BB&P’s final project shows a number of working places between 429 and 569.  Type A.4 offices (five modules of 7 m2) do not figure in the plans and are probably replaced by offices of type A.3 (four modules of 7m2).

174.	It should be noted that the figure of 569 working places is only achieved by compressing occupancy, that is, by accommodating four people in a type A.4 office instead of one and three people in a type A.3 office instead of one.  Given the disappearance of the A.4 offices mentioned above, the figure of 569 would have to be reduced to 554 working places at most.

175.	The real office capacity of the new complex can therefore be put at between 429 and 554 working places (an average of 500 places), which would be sufficient to meet needs in the optimistic scenario, but not in the pessimistic, which would have a shortfall of 60 places.

176.	It should be pointed out that closer studies of the plans of the final project reveal a capacity of about 1,000 office modules of 7m2, whereas the specification of the competition called for 1,285. There is no document that affords any explanation of this step.

177.	Conference room

The room does indeed have a capacity of 600 seats.  However, its subdivision has been changed from 150/450 (in the Competition) to 280/320, on an unspecified date and for an unspecified reason.

178.	Storage areas

These are considerably larger than stipulated in the specification.  Thus the archives comprise an additional 1,700m2 and the storage areas a further 4,485m2.  In our view, this major difference can only be explained by a future reassignment of certain areas as parking space, in response therefore to the original demands of Member States.

179.	Parking places

As mentioned above, the number of parking places in the new complex should be between 265 (optimistic version) and 387 (pessimistic version).  For the record, it should be noted that in the optimistic version WIPO continues to rent the P&G building, which contains 275 parking places.

180.	Since the new complex allows for the addition of 280 extra places, the needs of the optimistic version are covered, whereas in the pessimistic version there is a shortfall of 107 places.  These could be found by reducing the excess storage areas.

4.8.2	Civil engineer

181.	The documents made available for this audit were those showing the status of the project as of the end of November 2001, which corresponded to 100% of the pre-project contributions and 60% of the final project.  The remaining 40% will allow the initial estimates to be finalized.

182.	Analysis of the load-bearing structure of the new building and the additional storage has enabled us to confirm the choices made by the civil engineering contractor.

183.	The methods accepted for the surrounds of excavation and the excavations themselves appear suitable, given the types of terrain and the environment.  The load-bearing reinforced concrete structure consists of floor slabs supported on pillars or cross walls.  This choice is economical and gives great flexibility for the internal arrangements.  However, the positioning of some of the pillars which are not centered could cause complications and incur extra cost.

184.	The positioning of parking places on levels –3 and –2 is dictated by the structure of the upper floors.  Although some loads have been spread by means of crossbeams in the floor on the first basement level, we note that traffic movements in the car park are awkward and would require additional analysis.

185.	As for the conference room, the documents in our possession indicate that the project is not as far advanced as the other two parts of the work.  The plans seem to indicate that the load-bearing structure of the roof consists of a framework of non-rectilinear metal beams.  This seems to be a good choice, given the expressed architectural wishes.  The level of detail does not allow an accurate estimate of construction costs, so a broader approach, based on a price per m3 in other similar projects, needs to be considered in order to verify the overall budget for this feature, estimated at approximately 28.2 million francs.

186	As for costs, the adviser provided an estimate in summary form of all the civil engineering costs for the new building, the additional storage areas and the conference room.  The figure of approximately 40 million francs, estimated by the BB&P architects, was confirmed to within approximately 10-15%.

187.	The additional storage areas were also taken into account when estimating the three main headings (surrounds of excavation, the excavations themselves, concrete and reinforced concrete structures).  The total cost of the work estimated by the contractors in November 2001 was approximately 11.5 million francs.  Compared to the expert’s estimates, this figure is over-valued by about 30%.  The work to protect the surrounds of excavation and the excavations themselves is over-valued by about 40%, and that for the concrete and reinforced concrete by about 25%.

188.	The mezzanine at ground-floor level, the removal of floor slabs on the first floor, the excessive thickness of the slabs in places on the second floor and the crossbeams on the first basement level are the effect of the chosen architectural concept.  The additional cost of these specific elements can be put at approximately 1 million francs.

4.8.3	Heating, ventilation and air conditioning (CVC) Engineer

189.	The documents made available to the expert did not allow him to identify the chosen energy design, which must reflect the latest standards in technical know-how.  The studies demonstrated that the standards proposed for heating and cooling do not meet WIPO’s wish that the latest in building technology be used.  There is thus no correspondence between the image of modernity created by the architectural design of the planned project and that provided by the heating and cooling systems.  For example, the air curtain technique, used at the entrances of shopping centers some 20 years ago to keep out the cold is no longer in common use.  Similarly, the decision to use a four-pipe ventilator-convector design with cooling by ventilation does not conform to current standards for an office.

190.	The CVC (Heating, Ventilation and Air Conditioning) expert also deplores the lack of synergy with the heating and cooling systems of the existing building.

191.	Comparison of CVC equipment costs was made by reference to two buildings in Geneva, namely the HCR and WMO buildings.  This comparison was expressed in terms of the cost of an office module.  The costs of the WIPO installations were thus seen to be 43% higher than in the reference buildings.  This significant difference may be explained by the demands of WIPO (flexibility, individual CVC control of each office, glass façade), as well as by the chosen climatic design (ground-level convector, cold ceiling, forced air, extraction by superpressure in the reception areas), which is the most costly option.  An active floor design (where the floor ensures basic heating in winter and basic cooling in summer) would be less costly and ought to be considered.

192.	A new study of the climatic design of the conference room should be undertaken.  It is important to analyze whether it is wise to use ventilation for all heating and cooling demands, since conveying energy (for heating or cooling) using air is costly.  As for the conference room, the costs of the air-conditioning installation are 10% lower than those of the reference building (Salle William Rappard).

193.	Regarding the extra storage areas and the small amount of heating to be installed, the cost of this installation should not exceed 0.5 million, although it is put at 0.7 million in the November 2001 estimate.  The airflow calculation should also be revisited.

194.	The information supplied in relation to the November 2001 project was not what one would expect to receive for a pre-project.  Also, the documents we consulted in relation to the overall estimate were also more in keeping with a pre-project than a final project.  Moreover, a lack of coordination was noted between the various contractors.

4.8.4	Building phyisicist

195.	With its outer fabric of huge glass bays, the building corresponds to the architectonic idea of how a modern administrative complex should look.  The same goes for the large covered reception areas.  These qualities have already been recognized by the Competition panel.

196.	From the physical point of view, the structural design of the project conforms to the ideals of compact form and having the load-bearing structure located on the warm side of the building’s insulated shell.  The solar protection on the outside is also worthy of positive comment.

197.	The heat insulation of the project meets legal requirements.  However, as regards power consumption for heating and cooling, it is not exemplary.  In fact, legal requirements are only just met as far as the administrative building is concerned, while the conference room actually falls 10% below them.  For the project to be exemplary, standards such as the Swiss “MINERGIE” standards would have to be applied in order to guarantee an optimum level of comfort while being economically competitive and using energy resources rationally.

198.	The large glazed areas on the façades and built into the ceilings of the common areas will be a source of discomfort in both winter and summer.  These can however be remedied with appropriate heating and cooling installations, although this does involve higher installation and power costs.  In fact, given the large expanses of glass, it has to be expected that the additional power consumption for heating and air conditioning will exceed 10%.

| In winter | A feeling of cold caused by the radiation of body heat against the large, relatively cold window areas Internal air circulation (draughts) caused by falling air chilled by contact with the glass roofs |
| --- | --- |

These problems can be avoided by placing heating equipment under the glass surfaces.

| In summer | Overheating due to solar radiation |
| --- | --- |

199.	The heating, ventilation and air conditioning engineers recognized the problems and analyzed them using complex programs simulating the building’s power consumption.  The external solar protection greatly contributes to reducing this problem.

200.	Buildings with huge expanses of glass (more than 30% of the façade) represent a large proportion of new buildings in Switzerland.  Owners, authorities and planners are currently very sceptical, since a number of buildings have been built that have not been high on comfort or energy efficiency.  This is why the Federal Energy Office (OFEN) has ordered a research program with the object of establishing regulations for structures with huge expanses of glass.  The initial results are known, but have not yet been published.  It is strongly recommended that planners make contact with this study group in order to benefit from the results of their research (see reference 16).

201.	From the physical point of view, the structural design of the conference room conforms to the ideals of compact form and having the load-bearing structure located on the warm side of the building’s insulated shell.  The solar protection on the outside is also worthy of positive comment.  Compared with a traditional shape, the dual-curve free form incurs additional costs.

4.8.5	Plumbing engineer

202.	The adviser notes here too a mismatch between WIPO’s desire for a design based on the concept of the latest in technology and the standard proposed for the plumbing installations.  It would therefore be advisable to carry out more detailed investigation, jointly with the CVC engineer, into hot water production for the plumbing installations.  In fact, heat recovery on kitchen refrigerators and air conditioning refrigerators, use of solar power and decentralized hot water production are all options that reflect the latest standards in plumbing technology.

203.	The number of plumbing installations on the office floors is higher than the norm.  Also, fire hydrants have been provided in conjunction with a sprinkler system (spray nozzles which trigger automatically when the ambient temperature reaches a certain point).  This overlap serves no purpose, since if fire hydrants are installed there is no need for sprinklers, and vice versa.  With this in mind, a cost reduction of 15% could be achieved.

204.	As regards the next phases of the project, it is important to establish a design for hot water production for the plumbing installations which reflects the latest know-how.  The number of plumbing installations should also be reviewed in conjunction with the architect’s office, the fire protection system should be defined precisely, the usefulness of the water recovery system in the conference room should be reviewed, the standard of the professional kitchen should be defined and finally the costs arising from these proposals should be revisited.

205.	As regards the progressof the planning for plumbing installations and coordination between contractors, the same observation can be made as for the CVC installations (paragraph 194).

4.8.6.	Electrical engineer

206.	Defining the design and finalizing the client’s requirements form the basis of the work that drives the implementation of a project.  This is a very important phase, which must be carried out from the outset of the study and planning activity.  Apart from the document “Non-Exhaustive Questionnaire on Electrical Installations at the Pre-Project Stage” of June 2001, the expert does not know whether other such documents were produced.

207.	At this stage of the project, various choices and important decisions remain to be made in consultation with the client and the user (criteria for choosing a back-up electricity production method, principle for back-up power distribution, design of lighting and lighting management, principle for emergency lighting, universal cabling distribution design, IT network security design, general security design, design of technical management of the building).

208.	According to the documents of the overall estimate of March 2002, consulted for information, the expert considers that the state of progress of the studies does not completely match the level of an overall estimate.  Moreover, there is a lack of documentation to indicate how the studies for the electrical installations evolved.

209.	The expert did not find evidence in the documents made available to him to confirm that the techniques proposed conform to Swiss standards (SIA 380/4) and to the “Minergie” concept (energy efficiency in buildings). This point relates to a request made by WIPO (see 4.1).

210.	In general terms, the proposed project does conform to the requirements of this type of building, but certain technical choices could be improved.

211.	As mentioned in chapter 4.3, Context and WIPO objectives, the project must provide for “a complex of modern buildings, able to meet the needs of WIPO”.  Some of the proposed installations do not come up to the future-oriented technical level desired by WIPO.  They must therefore be improved.  For example, the infrastructure of a modern building requires high-performance computer cabling.  In view of rapidly evolving office automation needs, it would be highly advisable to plan for higher-performance cabling (broader bandwidth, at least category 6).

212.	IT network security must also be revisited, even completely overhauled.  The technical management of the buildings, as well as the organization and setting of technical alarms must be finalized.  Lastly, the organization of maintenance must be quickly addressed.

213.	The likely cost of the proposed electrical installations is within a range comparable to that of other administrative buildings similar to the WIPO project.  However it is low by comparison with other buildings of a high technical standard.  This is particularly so considering that the building in question would have to be of a high technological quality.  The real overall cost, after finalizing the various details, could be higher.

214.	Regarding the conference room, analysis of the costs confirms that the sum indicated reflects a reasonable average value.  However, in the absence of a definition of various pieces of equipment and systems, the range of possibilities when the installations are actually implemented remains wide open.  The costs could therefore vary considerably.

215.	Comparison of costs with three reference buildings (head office of a large telecoms company in Berne with 1,000 working places, administrative building and accounting center of the Federal Government in Berne with 500 working places, and the UNHCR administrative block in Geneva with 720 working places) confirms our impression that there was not enough leeway in the cost calculations in the November 2001 pre-project document.  Moreover, the average price per working place for the WIPO building is very high, as a result of the poor ratio of working places to gross floor area.

216.	The lack of specific detail in the definition of equipment provided for in the descriptive part of the November 2001 pre-project document creates a risk of additional cost, and consequently of a budget overrun.  It is therefore important to ascertain the impact on the budget of every design modification.

217.	When the project is being finalized, before preparing the documents for the call for tenders, it is vital that the client and the users ratify the various principles and designs.

218.	In the view of the expert, no precise specification exists for the “electrics” project.  It seems that the electrical contractor completed his project on the basis of a series of discussions with the client and the users, but those discussions were not documented.  It would be advisable for the engineering contractor to specify what electrical installations and equipment are provided for in the November 2001 overall estimate.

219.	Finally, the expert points to a lack of basic technical coordination between the various contractors.

4.8.7	Sound engineer

Conference room:

220.	He recommends using the present WIPO premises as a reference and carrying out an audit of their present acoustic status (sound insulation between different areas, sound insulation of façades, reverberation time in each location, noise level, etc.).  A survey of user satisfaction or dissatisfaction would also be advisable, as would an assessment of any specific acoustic requirements.

221.	The sound engineer noted that the specification for the outer fabric of the façades is overstated by about 10dB (according to the Federal Noise Protection Order and the Cantonal Ecotoxicology Service).  Consequently, for “standard glazing” an improvement in insulation on this scale means an increase in construction costs of some 10 to 15%.  The same applies equally to the administrative building.

222.	The relationship between the volume of the room and the number of people is approximately 9 to 11 m3 per person (or approximately 6,200 m3). For a conference room with potential for other activities, this figure should be kept to 5-8m3 per person, so that the surfaces (ceiling and walls) can meet the requirements for reverberation time.  The volume of the room should therefore be reduced to approximately 6 m3 per person in order to improve the volume-to-surface ratio.

223.	The literature indicates that a ventilation system renewing 50,000 m3 of air per hour is envisaged. Renewal of this quantity of air requires very high-performance noise limiters. It seems that the reduction in volume of the room, as well as improving the acoustics, also reduces the air renewal requirement and lessens the obtrusive noise from the ventilators.

224.	The rake of the floor under the seats is rather too shallow for delegates to be able to see and hear well.  It is therefore advisable to increase considerably the slope where the seats are located (in relation to the podium).  This would allow volume to be reduced and visibility improved.

225.	It should be pointed out that the shape of the room in plan view is highly unsatisfactory as regards visibility:  It is not easy to see the Chairman’s podium, and the angle of visibility for the seats at the extremities is less than five degrees.  This is particularly unacceptable for the interpreters, who must have perfect visibility of the conference participants.  It should be borne in mind that good visibility and good verbal comprehension go hand in hand.

226.	According to the sound engineer, sound-damping materials need to be used in the conference room, especially a textile floor covering and padded seats.

227.	Based on experience, particularly in the case of the Salle William Rappard and the Arena-Palexpo room, mobile partitions do not achieve the level of DnTw > 40dB.  When two conferences with translation and headsets are taking place simultaneously, provision needs to be made for a single mobile partition of at least DnTw > 35dB, while in the case of simultaneous use for film (video or cinema) and conference (with headsets for translation), a double mobile partition of at least DnTw > 50dB would be needed.

Reception area

228.	The sound engineer mentions the matter of the false ceilings on the mezzanine levels, which pose the particular problem of being acoustically reflective. This means that sound reverberation will be a problem in the reception areas of the administrative building.  The acoustics between the offices and the mezzanine level will therefore be inadequate, and the confidentiality of the offices will not be guaranteed.  To remedy these problems, some work is necessary on the floors of all the reception areas.  This will entail an estimated additional cost of 1.5 million francs.  Improving the acoustics of the surfaces in the mezzanine areas only has a very small impact on the acoustics of the reception areas.

4.9	Analysis of costs

Comparisons made with similar buildings in Geneva show that the surface-to-volume ratio per working place in the future WIPO complex is too high.  The effect of this is to increase considerably the cost per working place and therefore the overall cost of the project.

229.	Analysis of the November 2001 estimate highlights a number of errors.  Since these represent about 1% of the investment, we did not consider it worth looking for detailed explanations. The document also fails to mention certain items normally taken into account (cost of reproduction work, mock-ups, insurance, etc.), and WIPO expenditure (auditor’s fees)), all of which add to the cost.

230.	The figures calculated in this document refer to inclusive prices or ratios and do not seem to have been discussed with any commercial businesses, which increases the risk of inaccuracy.

231.	Lastly, at this stage of the studies, the estimate should clearly identify the elements that are not included, so that WIPO is aware of them.

232.	For purposes of comparison, we saw fit to consider the future administrative building alongside four comparable reference sites in the Geneva region.  These are as follows:

- WMO building, Geneva (overall estimate)

- HCR building, Geneva (final accounts)

- Salle William Rappard, Geneva (final accounts)

- Du Pont de Nemours building, Geneva (final accounts)

233.	The WMO and HCR buildings were chosen for their geographical proximity to the future complex (similarity of site and context), and also because they have programs that are similar to those of WIPO.  The Salle William Rappard is the only recent reference available for comparison, being of a similar size to that intended for WIPO.  Finally the Du Pont de Nemours building has features (volume, inner reception areas, etc.) in common with the future complex, while at the same time serving for comparison with a private business.

4.9.1	Comparison of prices per m3 SIA and m2 GFA, all CFC combined

GFA: Gross Floor Area

CFC: Code des frais de construction (construction costs broken down into nine groups)

234.	It is clear from table 8 below that the overall price per m3 of the WIPO complex is comparable to that of the other projects analysed.  Analysis of prices by m2 GFA confirms this fact (table 9).

235. Table 8. Comparison of m3 SIA prices, all CFC combined (including fees)

236. Table 9. Comparison of prices per m2 GFA, all CFC combined (including fees)

237.	On analysing each part of the project in greater detail, the cost of independent storage areas was found to be abnormally high (707 francs per m3 SIA, 2,197 francs per m2 GFA).

238.	The cost of the conference room is comparable to that of the Salle William Rappard, which is a room deemed to be of high quality.  However, the uncertainty regarding the progress of that part of the project and the rather unclear intentions of the architects lead us to express reservations.  These should however be covered by the overvaluation of the storage areas mentioned above.

239.	I consider that the budget anticipated at this stage is adequate for the completion of an administrative building, conference room and separate storage areas of the quality desired by WIPO. I would however draw WIPO’s attention to the degree of accuracy of the estimates for the final project stage (see table 7, paragraphs 248 and 249).

4.9.2	Comparison of prices per m3 SIA and m2 GFA, CFC 2

(Administrative building, extra storage area and conference room)

SIA: Swiss Association of Engineers and Architects

GFA: Gross Floor Area

CFC: Code des frais de construction (construction costs broken down into nine groups)

CFC 2: Costs relating to the building

240. Table 10. Comparison of SIA m3 prices per CFC (without fees)

241.	Detailed analysis of the SIA m3 price of CFC 2 (building) shows that costs for CFC 20 (excavation) and CFC 24 (heating, ventilation, air conditioning) are above average compared with the reference projects, while costs for CFC 25 (plumbing installations) and CFC 26 (transport facilities) are below average.  Detailed explanations for these differences can be found in the analysis by the advisers responsible for the relevant areas.

242.	CFC 22, which generally covers façades, is also very low (approx. 60 francs per m3 instead of 120 francs per m3 for the other reference buildings).  This fact is not explained, bearing in mind the high architectural demands (façades made entirely of glass, double skin in places) and technical demands (large glazed areas, large areas of blinds).  Analysis of costs per m2 confirms these differences.

243. Table 11. Comparison of prices per m2 GFA per CFC (without fees)

4.9.3	Comparison of prices per m3 SIA and m2 GFA

(conference room)

SIA: Swiss Association of Engineers and Architects

GFA: Gross Floor Area

CFC: Code des frais de construction (construction costs broken down into nine groups)

244.	This analysis shows that overall the price per m3 is comparable to that of the Salle William Rappard, both in terms of the total figure of Fr 812 per m3 for CFC 2, and in terms of the breakdown.

245.	Table 12. Conference room – Comparison of prices per m3 SIA per CFC (without fees)

246. 	In view of the high quality of the Salle William Rappard, the amount of the estimate for the WIPO room seems adequate.  Analysis of the price per m2 confirms this view (see reference 10, table 13).

247. 	It should however be borne in mind that this part of the work is at a less advanced stage than the rest of the project.  The degree of accuracy of costs is therefore lower, as table 7 below demonstrates.

4.9.4	Risks

248.	Table 7. Accuracy of cost estimates in relation to project progress (diagram based on experience of the project review expert)

249.	The table below summarizes the risks associated with the different rates of progress of the various parts of the project:

|  | Parts of the project | Total in millions | Accuracy in % | Risk in millions |
| --- | --- | --- | --- | --- |
| Administrative building | Technical installations (heating, ventilation, plumbing and electricity) | 29.4 | Pre-project stage -10% / +20% | -3 / +6 |
| Conference room | Room + technical installations | 28.1 |  | -2.8 / +5.5 |
| Extra storage areas | Technical installations (heating, ventilation, plumbing and electricity) | 1.3 |  | -0.1 / +0.3 |
| Administrative building | Building (without technical installations) | 102.6 | Final project stage -5% / +10% | -5 / +10 |
| Extra storage areas | Storage areas (without technical installations) | 18.5 |  | -1 / +1.8 |
| Total |  | 180 |  | -11.9 / +23.6 |
| Total admissible according to SIA standards |  |  | -10% / + 10% | -18.0 / +18.0 |
| Total according to market standards |  |  | -5% / + 5% | -9.0 / +9.0 |

Percentages indicated are based on the experience of the project review adviser
	SIA : standard of the Swiss Association of Engineers and Architects

The degree of precision allowed by the Swiss (SIA) standards at the final project stage is +/- 10%.  The table above shows that only the administrative building and the additional storage area (excluding relevant technical installations) meet that standard.  The other parts of the design (conference room, technical installations of the administrative building and additional storage areas) do not correspond to final project status but rather to pre-project status.  Consequently I have worked out that the allowable share of risk is +24 million francs instead of +18 million francs, according to Swiss standards, or +9 million francs according to market standards.

250.	In relation to the above-mentioned risks, it would be appropriate also to consider the following factors that could have an impact on the costs:

- Car park study incomplete

- Façades underestimated

- Coordination between technical contractors incomplete

- Estimate based on reference prices, not on a specification

251.	Moreover, the total cost of heading No. 5 in the November 2001 estimate, relating to “other secondary costs,” is 5.7 million.  The detail of this figure has not been specified, so I am not in a position to be able to verify whether this sum includes the elements below.  However, from experience this item normally represents 5% of total costs, which in this instance makes 9 million francs instead of the 5.7 million allowed for, i.e. 3.3 million francs more.

| Costs of obtaining authorizations and levies which could represent additional costs in the order of: | +1.5 million francs |
| --- | --- |
| Costs of reproduction work, mock-ups, documentation: | +1.5 million francs |
| Costs of travel, study visits, site surveillance and indemnification of neighbours | +1.0 million francs |
| Insurance | +0.5 million |
| Building site power |  |
| Bringing building on line |  |

252.	Finally the list below sets out the costs that are not included in the November 2001 final project estimate:

| Inflation |  |
| --- | --- |
| Interim interest payments, bank charges |  |
| WIPO Project Manager’s fees | +1.2 million |
| Project management fees (1% of the total cost) | +1.8 million |
| Audit costs | +0.4 million |
| Contractors’ fees for updating final project in the light of the audit |  |
| Removal expenses |  |
| Office furniture per gross working place (including infrastructure), furniture for conference room | +8.5 million |
| Total | +11.9 million |

4.9.5	Ratios per working place

253. 	For comparison purposes, an overall analysis was done of the volume and area per working place of the WMO, HCR, Du Pont de Nemours and future WIPO buildings.

254.	The graphs below show clearly that the SIA volume per working place is much higher in the WIPO building than in the other three.  This could be explained by the large volume set aside for the covered reception areas, and yet the graphic of gross floor area per working place (table 14) produces the same result, even though the reception areas are not included.  From this it may be inferred that the area per workspace is much too high in the WIPO building because of the size of the basement levels and public areas.  It therefore naturally follows that the comparison of cost per working place also shows a significant difference between WIPO and the other buildings.

255.	Table 14. Gross Floor Area (GFA) by working place

256. Table 15. SIA volume by working place:

SIA: standard of the Swiss Association of Engineers and Architects

257.	Table 16. Total cost by working place

258.	These ratios clearly demonstrate that the future WIPO complex has too much space set aside for representative areas.  Conversely, the number of working places is too low for the given volume and area.

259.	I am in a position to confirm that the budget envelope allocated to this project will allow it to be completed.  However, the area and volume per working place are too high and should be reviewed.

4.10	Conference room

    - Profitability

260.	The analysis is based on the following options:

- Scenario 1, representing the present situation

- Scenario 2, representing the approved investment of 15 million for a 400-seat room (see Sugden report and STG Coopers & Lybrand report);

- Scenario 3, representing the project under consideration, with an estimate of 30 million francs for a 600-seat room

261.	Construction cost per seat

Analysis of industry standards (benchmarks) shows that the construction costs envisaged by WIPO for a conference room are very high compared with projects that aim to be profit-making.  The proposed investment is 30 million francs for a 600-seat room (at 2 m2 per seat), or 50,000 francs per seat, whereas industry standards give a cost per seat of 24,000 francs (at 1.5 m2 per seat).  However, if one compares the cost per seat of this project with that of the Salle William Rappard, the costs are identical.

| Ratios | Scenario 2 (approved investment) | Scenario 3 (project under consideration) | Industry Standards |
| --- | --- | --- | --- |
| Average m2 per seat | - | 2.0 | 1.5 |
| Cost per seat (SFr) | 37,500 | 50,000 | 24,000 |

262.	Annual operating cost:

Based on the currently approved investment, the total operating cost is 1.1 million francs.  Under scenario 2, that cost rises to 2.25 million francs.

| Ratios | Scenario 2 (approved investment) | Scenario 3 (project under consideration) |
| --- | --- | --- |
| Annual financing costs (SFr)* | 675,419 | 1,350,838 |
| Annual maintenance costs (SFr)** | 450,000 | 900,000 |
| Total Operating Cost | 1,125,419 | 2,250,838 |

* based on depreciation over 40 years and 3.25% interest; interest + loan repayment

**up to 3% per annum – starting from the third or fifth year

263.	Rental cost of outside conference rooms:

The average annual cost of renting outside rooms during 2000 and 2001 was estimated by the economist at 0.75 million francs (40 francs per person per day).

| Ratios | 2000 | 2001 |
| --- | --- | --- |
| Minimum average cost per person per day* | 20 | 25 |
| Maximum average cost per person per day* | 35 | 40 |
| Total minimum annual cost* | 576,740 | 323,100 |
| Total maximum annual cost* | 1,009,295 | 516,960 |

* room rental + technical costs (board and lodging not included)

264.	Rental cost of outside conference rooms under three different scenarios:

| Scenario 2 (approved investment) (400-person room) 400-person room | 2000 | 2001 |
| --- | --- | --- |
| Number of outside conferences | 3 | 2 |
| Number of days of outside conferences | 46 | 15 |
| Number of participants per conference | 1,629 | 990 |
| Total participants | 25,890 | 7,870 |
| Total minimum annual cost (in francs) | 517,800 | 196,750 |
| Total maximum annual cost (in francs) | 906,150 | 314,800 |

| Scenario 3 (project under consideration) 600-person room | 2000 | 2001 |
| --- | --- | --- |
| Number of outside conferences | 1 | 0 |
| Number of days of outside conferences | 23 | 0 |
| Number of participants per conference | 626 | 0 |
| Total participants | 14,398 | 0 |
| Total minimum annual cost (in francs) | 287,960 | 0 |
| Total maximum annual cost (in francs) | 503,930 | 0 |

| Scenario 4 room for over 600 persons | 2000 | 2001 |
| --- | --- | --- |
| Number of outside conferences | 0 | 0 |
| Number of days of outside conferences | 0 | 0 |
| Number of participants per conference | 0 | 0 |
| Total participants | 0 | 0 |
| Total minimum annual cost (in francs) | 0 | 0 |
| Total maximum annual cost (in francs) | 0 | 0 |

265.	The annual operating cost of the new room according to the economist’s estimates would be 1.12 million francs per annum for a 400-seat room and an approved investment of 15 million francs, and 2.25 million francs per annum for a 600-seat room and an investment of 30 million francs.  Amortization of the investment has been calculated over 40 years.  The average annual cost of outside rental during 2000 and 2001 has been estimated by the economist at 0.75 million francs.

266.	The figure of 15 million francs for a 400-seat conference room does not seem realistic to me.  An investment of 20 million francs (50,000 francs per seat) should be considered in order to achieve the required quality.  This would increase the operating cost of the room from 1.1 million to 1.5 million (see scenario 2bis).

267.	According to the above estimates, the annual operating cost of the new room under the proposed project (option 3) would exceed by 1.5 million francs the rental cost of outside rooms at present (0.75 million francs in the case of a 400-seat room, scenario 2bis). From a strictly economic standpoint, therefore, the construction of a conference room of either 400 or 600 seats is not profitable.

268.	Summary of the various scenarios/options:

| Scenarios | Room capacity (seats) | Investment in millions | Operating costs in millions | Rental cost in millions | Total in millions | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 0 | 0 | 0 | 0.75* (0.3 – 1)** | 0.75 | Present situation |
| 2 | 400 | 15 | 1.1 | 0.2 – 0.9 | 1.3 – 2.0 | Investment of 15 million not realistic |
| 2 bis | 400 | 20 | 1.5 | 0.2 – 0.9 | 1.7 – 2.4 | Corrected investment |
| 3 | 600 | 30 | 2.25 | 0 – 0.5 | 2.25 –2.75 | Final project |
| 4 | 650 | 30 | 2.25 | 0*** | 2.25 | At the present stage (pre-project), the room must be planned to allow its capacity to be increased without increasing its area, while reducing the average area per seat |

* 	Annual cost of outside rental during 2000 and 2001, increased by a percentage for miscellaneous costs (transport, etc.)

**	Costs more or less identical to option 2, since large conferences are spread over several days and have over 400 participants

***Calculated on the basis of the last two years. Meetings (unforeseeable above 650 places will have to be organized by linking the two rooms (250 + 650 = 900 spaces) or held externally.  In the latter case, the rental costs would have to be added to the operating costs.

269.	As shown in the table above, there are thus four distinct options:

- Option 1: This option reflects the present situation.  WIPO has to rent a room elsewhere whenever the attendance at a conference exceeds the current capacity of room A.  Not building a new room at all seems to the economist to be the most defensible of the proposed options from a strictly economic standpoint.

- Option 2: Principle approved by the Member States to build a 400-seat room at a budget of 15 million francs. On the basis of the Salle William Rappard, we note that this budget is not realistic.

- Option 2 bis: Value of the investment for option 2, corrected on the basis of the final accounts of the Salle William Rappard in today’s money.  A 400-seat room is too small to meet the real needs of WIPO.  This option would therefore oblige the Organization to continue to hold many conferences elsewhere, and would in the view of the economist be an investment that made little sense.

- Option 3: Project for construction of a new room as set out in the BB&P documents.  Building a 600-seat conference room means investing 30 million francs with the virtual certainty of having to organize future WIPO General Assemblies elsewhere.

- Option 4: The economist’s proposal is to build a room with a capacity of greater than 600 places for a budget equivalent to that of the project presented.  This option would correspond to WIPO’s aims and future needs.  It does however entail a reduction in the average area per delegate.

4.10.2	Justification of future needs

Changes in the number of participants in WIPO meetings:

270.	Analysis of conferences organized by WIPO up to the end of 2001 shows that the number of conferences has remained stable (between 45 and 57 per annum): the WIPO report (Report II, Needs for a Conference Room, March 4, 2002) mentions an estimate for the year 2010 of more than 60 conferences during the year (as against 45 in 2000), lasting a total of 260 days (against 240 in 2000).  Conversely, the number of participants has trebled in ten years (from 2,209 in 1991 to 6,587 in 2001).  Approximately 40% of the conferences took place elsewhere (45% in 2000 and 38% in 2001), which corresponds to nine in 2000 and eight in 2001.

271.	The economist’s analysis shows that if WIPO were to decide to build a conference room that would be used by the Organization on average 50 days per year for approximately eight or nine conferences, it should in any event be able to be used for the WIPO General Assemblies.  Its capacity should therefore be planned to exceed 600 seats.  It will indeed be a conference room for the future, intended first and foremost for the Organization’s General Assemblies, which already have an attendance of 584 today.

272.	Moreover, for a 400-seat room, WIPO would have to set aside between 1.7 and 2.4 million francs (option 2bis, average of 2 million francs) for the operating costs of the new room and the cost of outside rental.  This represents an additional cost in relation to the current situation of 0.95 to 1.65 million francs (average 1.25 million).  However, for an operating cost estimated at 2.25 million francs, equating to 1.5 million francs more than at present, it would be possible to obtain a 650-seat room that could house not only the annual General Assembly in a single room, but also the vast majority of other conferences organized.  This figure does not include rentals for events of the Diplomatic Conference type requiring more than 650 seats, the frequency of which is not known.

273.	The project review adviser, with the help of WIPO, has identified more than ten different types of meeting that have an attendance of more than 100.  This has allowed three representative groups to be formed:

1.	General Assembly of Member States. This group is characterized by a regular, consistent increase in attendance:  the number of Member States has gone from 158 in 1995 to 178 in 2001.  The maximum participation by 2010 can be put at 185 Member States.  Taking an average of 3.2 people (the average number of participants per delegation), the number of delegates should be 590, plus about another 30 intergovernmental organizations (IGOs) and non-governmental organizations (NGOs), each represented by two people, making a total of approximately 650.

2.	Standing Committee.  The standing committees are characterized by working meetings at regular intervals with between 150 and 300 participants.  The Diplomatic Conference that approves the results of these working meetings has a higher attendance.  In fact, since the Member States are often all represented, the IGOs and NGOs attend these meetings in greater numbers.  For Diplomatic Conferences organized at undefined intervals, participation will very much depend on the subject.  If the subject is weighty or if it has to with a number of treaties, it can attract a very large audience, as in December 1996 (772 participants).  In the future, it is likely that WIPO will still have to rent a room elsewhere when the subject attracts an unusually large audience.  However, the meetings are called at least six months in advance, which gives time for a location to be found before the date is announced.

3.	One-off events.  Attendance at these events cannot be forecast and depends greatly on the subject.  For this type of meeting where taking the floor does not have political significance, it seems possible to organize two linked rooms, which allows the audience to be placed in rooms close to one another and thereby considerably increases capacity (in this instance, room A and the new room).

Only group 1 allows the room capacity to be determined. Ideally it should be 650 people.  Looking at the last ten years, one notes that this would have been sufficient for the very great majority of WIPO conferences (two conferences would have had to take place outside).  It would also allow the Organization to hold its annual Assembly there.

Ideal capacity of the conference room:

274.	The ideal number of seats should at least allow the annual General Assembly of WIPO to be held, as well as the large majority of other conferences organized.  Attendance at other types of meeting depends on the subject matter and cannot be predicted.

275.	It emerges from analysis of the conferences organized during the last ten years that they break down into three types:  those with 100 to 200, 200 to 450 and 450 to 650 participants.  Conferences with more than 650 participants generally come under the heading of “Diplomatic Conference” or “one-off event,” attendance at which is impossible to predict.

276.	Overall, the construction of a room with a capacity of more than 250 seats (capacity of the present room) will relieve the pressure on room A.  The planning carried out for the years 1999 to 2001 (see reference 11), with a new 400-seat room, shows that one to three meetings a year would have to be organized outside the confines of WIPO.  Those meetings would include the annual General Assembly of the Member States.  By building a room with a maximum capacity of 650 seats, the analysis shows that WIPO would have had to organize two meetings outside (a Diplomatic Conference in 1996 and a one-off event in 1999).  The possibility of subdividing the 650-seat room into two rooms of 200 and 450 seats affords added convenience:  this allows the room to be adapted to the size of the conference, which improves the working environment (a full room is more motivating than a large room half-empty).  Moreover, this subdivision increases the opportunities for rental.  A 650-seat room will be occupied more often than a 400-seat room (conferences with more than 400 persons would have to be organized elsewhere).  However, if this 650-seat room is not divisible, it will often be too big for the event being held.

277.	Taking account of the investment that would have to be agreed, the construction of a 650-seat room, divisible into two rooms of 450 and 200 seats, offers the best balance between overall annual cost and flexibility of use.  For events with over 650 participants, WIPO would have to continue to rent a room elsewhere or organize linked meetings by connecting the new room to room A, which will give a total capacity of 900.

Division of the room:

278.	The additional cost represented by the installation of a partition is certainly considerable (1.5 to 2 million francs).  However, such a partition is in my view necessary for the following reasons:

- The ability to divide the room will allow WIPO to adapt the size of the room to the number of participants, particularly for meetings with 300-450 participants.  Since the room is a working facility, this seems to us an important motivating factor for the delegates.

- Allowing subdivision greatly increases the availability of rooms and therefore the opportunity for rental.

- According to WIPO forecasts, conferences for between 100 and 250 participants are increasing more rapidly than the others.  The subdivision of the room will allow this trend to be catered for.

- The statistics available to WIPO do not allow an assessment of the phenomenon of plenary sessions with sessions in working groups during breaks. In the view of WIPO, this way of working is on the increase and requires the availability of a larger number of small rooms.

Expected Investment

279.	At the present stage of the project (pre-project for the conference room) it should be possible to increase slightly the capacity of the room, but without increasing its cost, by adopting one or a combination of the following measures:

- Reduction in the average area per delegate seat.  The ratio of net m2 per delegate provided with a desk ranges from 1.7 m2 for the Salle William Rappard to 2.0 m2 for WIPO room A and CICG Room No. 2.

- If one assumes that a minority of participants (about 30%) are considered “observers” and do not have a desk, one could reduce the average area per delegate.  For delegations of more than two persons (50% of delegations), it might be possible to arrange for some of them not to have a desk.  So a five-person delegation would have only three seats with desks, microphones and headsets, while the other two seats would be immediately alongside but would have only headsets.  This arrangement, if ratified by WIPO, could make it possible to reduce the average area per participant (in this case from 2 m2 to 1.6 m2 per seat).

280.	The operating costs of the new room could be partly covered by renting the room to outside organizations when it is not in use by WIPO, which is frequently the case.  In fact, analysis of the conferences organized by WIPO in the last ten years shows an increase in the number of participants, rather than in the number of conferences, which has remained very stable.  That is why, if WIPO were to decide to build its room, it seems to me essential to set up a commercial department to manage the three WIPO conference rooms.  By way of reference, we once again mention WTO, which rents the Salle Rappard (710 seats) at 7,000 francs a day, as well as WMO, which rents its 260-seat room for 2,900 francs a day and its 70-seat room for 600 francs a day.  These rooms have the same capacity as the three rooms that WIPO could rent out in the future.

Market survey – conference infrastructure in Geneva (see reference 18)

281.	In response to the request made to me by the Member States of Group B at the presentation meeting on February 22, 2002, I have have arranged for the economist to  carry out a market survey of the available conference infrastructure in Geneva.  It emerges from this study that the facilities that meet the needs of WIPO (600-seat or larger rooms) are the following conference centers or hotels: CICG, Palexpo, President Wilson Hotel, Salle William Rappard and UNOG.  As a general rule, owing to the small number of rooms available, room reservations for the above capacity in Geneva have to be made between 12 and 18 months in advance.  Events in this city generally take place during the same periods of the year, which adds to the problem of the lack of infrastructure and complicates the reservation problem.  As for the cost of renting outside conference rooms, the hotels quote a rate almost double that quoted by the conference centers.  Annex 2 of the economist’s report gives details of the infrastructure and rental costs of the available rooms in Geneva.

5.	PROJECT ORGANIZATION

282. 	At the request of WIPO, various proposals for organizing and implementing the project were studied by the Federal Audit Office and considered alongside other projects in Geneva (WTO/Salle William Rappard, ITU/new Montbrillant building, WMO/new building) (see reference 19).  Although other solutions do exist, it does not seem advisable to me, given the lack of a guarantee from the client, to use standard working procedures (individual contracts with companies and suppliers). On the contrary, implementation under a total services contract (see diagram below) seems to have greater appeal.

283. 	Organization diagram of a project under total services contract

(standard organization for large projects)

284.	I am of the opinion that a total services contract arrangement would be better suited to the implementation phase of the works.  Working in this way would allow conflicts to be avoided between subcontractors, given that they would be under the responsibility of the general contractor.  The client would ultimately have only a single partner in the implementation phase, a single person in overall charge, and a single contract.  The only reservation would be over the final project, which has to be planned in a very detailed manner in order to avoid overspends during project execution.  It would therefore be better to view the project in the context of economy and profitability, subject to respect for the architectural design.  The diagram proposed above represents a normal organization for management and implementation of a large project.

- The position of client’s representative should be a full-time role. The client’s representative should also have decision-making authority, so that decisions can be taken rapidly as project requirements dictate.  His first task would be to verify that the




various project and technical specifications are in keeping with WIPO’s needs.  This task will not allow a call for tenders to be made before the end of 2002.  In order to conduct a call for tenders with maximum cost certainty, one needs to be sure that the final project is actually finalized.

286.	Project management should be the responsibility of a company outside WIPO.  It seems to me sensible to divide the responsibilities between WIPO and the project manager, so that the client’s representative is better placed to specify requirements (costs, time limits, specification).  This company would act as an assistant to the client and would provide the following services:

- Management of project quality

- Verification of project conformity to specification

- Risk assessment in each phase

- Coordination of planning and implementation processes

- Monitoring of negotiations and award of contracts

- Management of contracts, modifications, riders, time limits and costs

- Etc.

287.	The diagram below shows the opportunities for modification of the project (in red) and the increases in costs (in blue) in relation to the various phases.  It is clear that modifications occurring later than phase 4 generate significant costs.  This is why the final project (phase 3) must meet the client’s specification in full and must include all the requirements with the utmost precision, in order to minimize as far as possible the risks of defects at the time of implementation, which could cause considerable additional expense.  This is particularly true when working under a total services contract.  Indeed, experience has shown that every rider to a basic contract brings with it high costs that are often well in excess of market prices.  These observations lead me to recommend that implementation of the call for tenders for a total services contract should not occur before the end of 2002, in order to be able to incorporate the comments of the evaluation report on the new building and thereby to update the final project.  The call for tenders for the management of the project would have to be done after submission of my report to WIPO, so as to incorporate the updates made to the final project in the specification.

6.	INVENTORY OF POSSIBLE SAVINGS AND OTHER TECHNICAL SOLUTIONS PROPOSED BY THE VARIOUS ADVISERS

The paragraphs below summarize succinctly the other technical solutions raised by the various advisers.  For further detail, refer to the experts’ reports (see references 13, 14, 15, 16, 17).

6.1	Inventory of technical solutions

288.	Heating, Ventilation and Air Conditioning (CVC) Engineer

- Heating and cooling

(a) Administrative building:

Study possible synergies with the existing building (central power generator).  A cheaper option than the proposed solution (floor-level convectors, cold ceiling, forced air, extraction by superpressure in the reception areas), which moreover no longer reflects current standards, providing the same advantages (flexibility, individual control), could be considered using the following principles:

  - Active floor providing (basic) heating in winter and (basic) cooling in summer.

  - Warm ceiling in winter and cold in summer

(b) Conference room:

  - A water system satisfying heating and cold ventilation needs.

- Ventilation

(a) Administrative building:

  - Reduction of 30% in the forced air output by superpressure extraction in the reception areas.

The “four-pipe ventilator-convector, cooling by ventilation” concept is no longer standard CVC equipment for an office.

(b) Conference room:

The principle of a ventilation system that provides for all heating and cooling demands is no longer in common use.  The expert’s proposal is as follows:

  - Ventilation providing an airflow of 15 to 20 m3 per hour per person, which for 600 persons amounts to 9,000 to 12,000 m3 per hour.

- Environment

Consider the “Minergie” concept, which aims to guarantee a superior comfort level while being economically competitive and energy-efficient.

- Heat recovery

Consider the option of “de-superheaters” on refrigeration plant.

289.	Plumbing Engineer

- Hot water production

Decentralized hot water production for plumbing installations (hot water produced locally in an electric water heater).

- Solar power

Use of solar power for hot water production for plumbing installations.

- Heat recovery

Heat recovery on kitchens refrigerators and air conditioning plant.

- Rainwater recovery

Investigate the possibility of recovering rainwater from the roof of the conference room.

290.	Electrical Engineer

- Distribution design

In order to avoid disruption of the IT network, the vertical distribution and the distribution areas need to be arranged in such a way as to avoid telecom equipment and cabling being placed immediately alongside high-voltage equipment and cables.

- Environment

Take account of the “Minergie” concept.

- Production and distribution of emergency electrical power

No concept, requires study.

- Emergency lighting

No concept, requires study.

- Universal cabling distribution

No concept, requires study.

- IT network security

No concept, requires study

- Office lighting

Use of free-standing lamps fitted with sensors and daylight bulbs and linked to the building’s technical management installation.  This proposal would allow great flexibility of usage and would fit with the concept of energy efficiency.

- Low-voltage equipment

Study the functionality of the various proposed systems, especially their compatibility and interdependence.

- Telephone switchboard

Determine the need for the centralization of incoming calls and use of the computer network for telephony.

- Universal cabling

It would be advisable to provide for more powerful cabling with broader bandwidth, at least equivalent to category 6.  Moreover, the overall cost increase due to the use of fiber optics for all components would be offset by a 5% increase in capacity compared with the “copper cable” system chosen.

- Management of timekeeping, time clocks

With regard to time signals, we have to report the absence of any documentation or diagram relating to this installation.  It is important to define needs with the client and the user.

- Interphones

There is no mention of intercom and videophone requirements.

- Paging

A DECT telephone system is recommended in place of the conventional paging system proposed.  Use of portable DECT gives the user great mobility.

- Audiovisual equipment

For the reception area on the ground floor, there is a case for providing an electronic display system for visitor information.  A possible alternative for the building’s emergency evacuation system would be the installation of an alarm system via the telephone network, which would allow the broadcasting of pre-recorded or live messages instead of a siren and thereby prevent panic reactions.

- Conference room equipment

By interconnecting the conference systems control deck with the cabling of the building automation system, it would in principle be possible to manage several types of audiovisual presentation (lighting management, blinds, projection screens, video projectors and computer-controlled presentations).  Interconnection via the Internet must also be available (intercontinental link-ups, videoconferences).

- Building technology management

The diagrams of the principles of the proposed installations provide for command modules for the blinds and lighting control boxes in the false floors, organized by module and by office.  This technology does not offer the same options as the modern management systems available on the market.  New technology enables each consumer (lighting, blinds, etc.) to be linked on decentralized programmable automated modules.

- Alarm management

For a complex project such as WIPO, the alarm management functions must be handled by a well-designed system.  They could perhaps be integrated in the building’s technology management system.

- Access control

It would be preferable to choose a system integrated with the universal cabling.

- Fire detection

At this stage of the project, it would be wise to define in an outline diagram all the functions triggered by the fire detection system (fire doors, shut-off valves, emergency exits).

- Burglar alarm equipment

It would be advisable to know the specifications for the surveillance of the outside of the buildings and the link to the video surveillance system. It should also be ascertained  whether the safes are fitted with burglar alarms.

- Facilities maintenance

Early analysis of the question of maintenance will allow provision to be made for the installation of certain infrastructural elements.  Given the structure of the buildings and the height of certain areas, the option of buying a hydraulic cradle needs to be considered.  The cradle could also be useful for maintenance of the ventilationand fire detection systems, the video surveillance equipment and so on.

291.	Building Physicist

- Environment

Take account of the “Minergie” concept.

- Interior comfort in winter and summer

Owing to the large glazed areas, one could highly recommend analysing the building using a simulation program (for example, the program of the Federal Testing and Materials Laboratory).

292.	Sound engineer

- Volume

For the surfaces (ceilings and walls) to conform to reverberation time standards it would be necessary to reduce the volume of the conference room to 6 m3 per person, instead of the current 9 to 11 m3.

- Visibility

In order to improve visibility and therefore audibility for delegates, it would be necessary to increase considerably the rake of the floor where the seats are located (in relation to the podium).

- Noise

Reduce the obtrusive noise of the conference room ventilators.

- Acoustic treatment

Allow for highly sound-absorbent ceilings and walls in the reception area, covering a total area of about 4,500 to 6,000 m2.  Insulation from airborne noises between the offices and the reception area corresponding to at least 40dB is required, so the concept of trunk ventilation would be worth investigating.

6.2	Inventory of Savings

293.	Civil Engineer

- Excavations (for additional storage areas)

Since the work to protect the excavation areas has been overvalued by about 40%, and those for concrete and reinforced concrete by 25%, savings are possible in this area.

294.	Heating, Ventilation and Air Conditioning (CVC) Engineer

- Ventilation

Administrative building:

Reduction in airflow of 30% per element.  Looking at 1,000 modules, one notes a saving of 10,000 m3 per hour, or 250,000 francs.

- Heating

Replacement of floor-level convectors by heating units with the flexibility of two heating elements instead of one.

Reconsider the of the active floor, which would serve as a basis for heating and cooling. The ceilings (warm and cold) would provide back-up and regulation, using the principle of three pipes instead of four.

Extra storage area: in view of the airflow of 16,000 m3 an hour and the small amount of heating to be installed, the cost of this installation should be reduced by 0.2 million francs.

295.	Plumbing Engineer

- Fire protection installations

The overlap between the sprinkler installation and the fire hydrants means that a saving of 15% could be achieved.

- Kitchen

A saving of about 15% would be possible in relation to the demands of a professional kitchen.

296.	Electrical Engineer

- Lighting

Use of free-standing lamps in office spaces.

297.	Building Physicist

- Surfaces

A reduction in the percentage of glazed areas would have the effect of reducing building and operating costs (cost savings in the CVC installations and in the power consumption for heating and cooling).  This saving does however entail a departure from the architectural purpose of the project.

298.	Sound engineer

- Acoustic requirements

The reduction in acoustic requirements concerning the façades would mean a cost reduction of 10 to 15%.

PART III

Annexes

(WIPO – World Intellectual Property Organization)

- WIPO		Report I (Needs for Office Space and Parking)		11.04.2002

- WIPO		Report II (Needs for a Conference Room)		04.03.2002

- WIPO 		List of conferences organized in Geneva since 1990	21.03.2002

[Appendix 1 follows]

# Text boxes

11%

.

Conference room

Basement 43%

Offices 36%

Public areas 10%

Public and common areas
10%

Conference room 8%

Offices 23%

Basement and storage 59%

Cross-section of office building

representative areas – lounges

useful volumes

useful volumes

Project Manager (External)

IImplementation

DIRECTOR GENERAL

GENERAL ASSEMBLY

WIPO STRUCTURE

COORDINATION GROUPS

IMPLEMENTATION COMMITTEE

BUILDING CONSTRUCTION COMMITTEE

1 representative

1 representative

CLIENT’S REPRESENTATIVE

PRINCIPALS

Provision to be made in the tender documents for 1 technical manager paid for by OE to oversee the technical specifications

QUALITY & PROJECT MANAGEMENT

CONTRACTORS

EXTERNAL STRUCTURE

# OVERALL ENTERPRISE

(1 partner, 1 overall manager, 1 contract)

ENGINEERS

SPECIALISTS

CONTRACTORS

ARCHITECT

ASSISTANT ARCHITECT

Call for
tenders

Project
Studies

Preliminar
Studies

Definition of aims

Investment

Operational Phases

Strategic Phases

Opportunities for modifications

WO/PBC/5/3

ANNEX

Project Manager - Client

Total Services Contractor

Development of project management specification
with the help of a specialist

Updating of final project based on SFAO report

Creation of documents for call for tenders

Call for tenders and award of contracts

Aug. 2001
pre-project

June 24, 2002
SFAP report

END 2002