## Capabilities and capacities
New product development capabilities and capacities | [11 empty] | © 2017 KnowWare
Tangible features OR design requirements to realize core benefits sought | Make biofuel | Ease of use sensor and software | Delivery | Biomass for testing | Downstream organisms - adapted for mini-refinery system and/or for different types of biomass. | Feature or requirement 6 | Feature or requirement 7 | Feature or requirement 8 | Feature or requirement 9 | Feature or requirement 10 | Should-cost price
Tasking | License system and organisms. | Find sensors and software, and adapt them for remote operations, monitoring, and maintenance of our system. | Determine how to ship it to remote locations with poor road conditions. | Identify various sources from all regions to test a range of biomass from each target country. | Better organisms.
Labor skills | Production capability and ability to handle organisms. | Sensor engineer and software programmer | Logistics manager | Logistics and procurement | Research and development (R&D)
Know-how | How to work with the specific licensed organisms and optimize the operation of the mini-refinery. | Experience with the technology | Logistics and packaging | Nothing in particular | R&D
Supplies and materials | Vats, conveyors, chippers, mulchers, filters, valves, piping, storage tanks, and organisms. | Sensors and software | Crates or containers that can be loaded with equipment and connected together. | Crop or crop waste, other organic waste. | Not sure
Equipment and facilities | As needed to assemble the system, and to grow, harvest, and package organisms for shipping. Quality Assurance Lab to ensure that organisms and products meet required standards. This could be rented. | Ability to test sensors upon delivery of the mini-refinery unit, and to use a model for running the software. | An efficient way to build or acquire packaging. | Equipment for preprocessing. | Intend to find R&D partner if we pursue this.
Technology and intellectual property | Obtain licenses from the holders of IP rights for the organisms and methods, such as Remarkable Biofuels LLC or similar entities. If necessary, also acquire licenses for mini-refinery technology. | Obtain a license for the software. If adaptations are made, consider copyright or other data protection for the code. Additionally, if the adaptations are unique, explore patent protection for the changes implemented in the system. | Most likely none | Most likely none | Obtain a license from a university or research institution holding IP rights. If new organisms are developed, we may generate our own IP.
Working capital | Approximately USD 1 million for prototypes. | USD 500,000 | Depending on whether containerized, probably under USD 100,000. | Ideally, we can obtain this at no cost and only need to arrange pickup and delivery to the test site(s). Delivery charges should be under USD 25,000. | Uncertain; we may be able to secure government grants, such as small business grants or grants for biofuel research.
Vendors, contractors and partners needed | Sources for the equipment to be integrated | Sensors and software | Delivery company | Farms and waste collection facilities | University or research institution
Other factors | Need a regulatory expert to obtain any necessary approvals. Prepare manuals for biofuel production. | Manuals will be critical and the best way to handle the telecommunications aspect. | Hopefully, we can put this out for bid and have someone come up with a solution. | It is important to ensure we obtain a wide range of biomass for testing. | If we collaborate with a university or research institution, it would be beneficial to involve a graduate student who could potentially join us if the project succeeds.

## Action plan framework
| Steps involved and percentage of anticipated progress toward completion | [8 empty] | How it will be accomplished and how you will know it is done
Tangible features OR design requirements | Idea | Screen | Design | Development | Test | Launch | Post-launch | Totals | Stage | Key tasking | Who is responsible for completion | Completion milestone | Budget | Start and end dates
Cutting and mulching waste equipment | 5% | 20% | 20% | 50% | 5% | 0% | 0% | 100% | Idea | Determine the feasibility of sourcing necessary organisms, parts, components, and systems. |  | Validation that suitable organisms exist and can function in the mini-refinery. | USD 5,000 | 02/02/2021 - 20/02/2021
Brewing vats and capture tanks | 5% | 20% | 35% | 25% | 15% | 0% | 0% | 100% | Screen | Assess market, technical, and financial viability. | Market work: market research expert; technical viability: engineering expert and legal consultant; financial: finance and budgeting expert | Competitive advantage and freedom to operate established; confirmed feasibility of market entry for the product concept; Technology Readiness Level (TRL) 2 achieved. | USD 25,000 | 01/03/2021 - 25/05/2021
Cleanable filters | 5% | 20% | 20% | 40% | 15% | 0% | 0% | 100% | Design | Establish a Business Model Canvas; finalize the technical approach, secure organism licenses, and establish proof of concept; complete the design project in alignment with the model. | Business model canvas: team leader; technical approach and design: engineering and technical expert, and design consultant; IP and supplier/vendor qualification and contracting: logistics expert, with legal consultant | Business canvas model approved; licenses for organisms obtained; TRL 3 achieved; design approved; vendors/suppliers qualified and contracts in place | USD 100,000 | 01/07/2021 - 30/11/2021
Piping and valves | 5% | 20% | 35% | 25% | 15% | 0% | 0% | 100% | Development | Develop a benchtop prototype and an operational prototype; raise the remaining necessary funding. | Engineering and technical expert, with production engineering consultant | TRLs 4, 5, 6, and 7 attained | USD 170,000 through TRL 4. Additional USD 1.3 million as raised | 01/12/2022 - 28/10/2022
Conveyors | 5% | 20% | 20% | 40% | 15% | 0% | 0% | 100% | Test | Achieve all certifications and regulatory compliance; complete beta testing. | Engineering and technical expert and logistics expert, with legal consultant | TRL 8 and 9 attained; all necessary certifications and registrations received | USD 500,000 | 01/11/2022 - 28/03/2023
Fungi/organisms for biodiesel, ethanol, and hydrogen | 5% | 25% | 25% | 25% | 20% | 0% | 0% | 100% | Launch | Prepare manuals and train market and sales personnel, sales representatives, installers, and maintenance repair staff; implement a marketing campaign; establish corporate and retail sales channels. | Training: team leader with training consultant; marketing and sales: business development expert and sales and marketing department manager | Personnel trained for launch and support; marketing campaign implemented; sales channels established; initial revenue targets hit | USD 200,000 | 01/04/2023 - 28/08/2023
Controls for onsite and remote operations, monitoring, and preventative maintenance | 5% | 25% | 25% | 25% | 20% | 0% | 0% | 100% | Post-launch | Revise manuals and training materials as needed; enhance online training and support with improved software and platforms, if available and affordable; develop a list of desirable improvements, enhancements, and additions. | Product line manager. Team now acts as in-house consultants | Removal of product from sales plans | To be provided by product line manager as needed | 15/01/2024 - 30/12/2043
Sensors for onsite and remote operations, monitoring, and preventative maintenance | 5% | 20% | 25% | 25% | 20% | 0% | 5% | 100%
Software for onsite and remote sensors and controls for operations, monitoring, and preventative maintenance | 5% | 25% | 25% | 25% | 20% | 0% | 0% | 100%
Modularize for transport | 5% | 15% | 35% | 30% | 10% | 0% | 5% | 100%
Should-cost price | 5% | 15% | 40% | 20% | 10% | 5% | 5% | 100%
Time Line

## Notes and references
Notes:
Timing and budgets are based on interviews with team members and certified new product development professionals experienced with related products. The certification is from the Product Development and Management Association (PDMA). The tasking was developed by the team and reviewed with PDMA members during interviews to ensure it is reasonable and complete.
References: