## Slide 1
IAOD Evaluation Seminar
“Demystifying Evaluation in WIPO - Best Practices from Initial Evaluations”
Geneva
November, 8 2012
2012
Evaluation of Project „Developing Tools for Access to Patent Information“ – Key Lessons

## Slide 2: Purpose of this presentation
Briefly present the project we have evaluated;
Discuss the evaluation approach, evaluation steps and the methodology used;
Summarize the key conclusions and recommendations as far as they are of general relevance to WIPO and the seminar participants;
Share my personal experience in conducting my first evaluation assignment for WIPO – what worked well and suggestions for improvements;
Draw conclusions and make some suggestions for WIPO‘s future evaluation work.

## Slide 3: Summary of project that was evaluated
The evaluation of the DA-Project “Developing Tools for Access to Patent Information” was conducted by IAOD from July – September 2012 with my support as an independent consultant.
The Project with a duration of 30 months and a budget of CHF 1,576,000 started in January 2010. It aimed at “enhancing access of developing countries to patent information”, by publishing patent landscape reports, developing an e-tutorial and organizing regional conferences.

## Slide 4: Evaluative steps used
Analysis of Terms of Reference;
Desk study of documents and analysis of existing data;
One-day briefing with the Director of IAOD, the Evaluation Section and key internal stakeholders of the project;
Draft inception report („procedures for evaluation“);
In-depth face-to-face semi-structured interviews with internal and external project stakeholders (four days);
Discussion on preliminary findings, conclusions and recommendations with the purpose to get alignment with project stakeholders within WIPO;
Draft report (one week), obtain written comments, amend report.
De-briefing, integrating all comments into report (three days).

## Slide 5: Evaluation Approach
The emphasis of this particular evaluation was on organizational learning, while still ensuring the purpose of accountability.
The evaluation approach was interactive and participatory (discussion based on a list of guiding questions rather than driven by what the evaluator feels is important). The process itself was designed to contribute to continuous improvement of WIPO’s services.
The project was invited to participate in all interviews (prior consent of interview partners was obtained). There was no hidden agenda (e.g. instructions by IAOD on expected „findings“ or recommendations).

## Slide 6: Methodology
Assessment of project based on standard evaluation criteria (relevance, efficiency, effectiveness and sustainability of results) in order to provide a well-founded opinion whether the project provided the right type of support in the right way.
Different evaluation tools were combined to ensure an evidence-based qualitative and quantitative assessment. Particular emphasis was given to cross-validation of data and an assessment of plausibility of the results obtained.
The methodological mix included desk studies, literature review, individual interviews, interviews of focal groups and direct observation.

## Slide 7: Main conclusions of the evaluation
Conclusion 1: The project was generally well prepared and managed, but there is room for further enhancing existing tools for planning, monitoring and evaluating projects. WIPO does not have system to track users of online services.
Conclusion 2: The project design was clearly overambitious, especially for achieving the objectives set for the patent landscaping reports. The project duration seems to be driven by budgeting cycles, not by realistic estimates of the time needed to achieve objectives.
Conclusion 3: While the project overall provided the right type of support in the right way, not all of its expected outputs were delivered. It was not possible to assess outcomes, impact and potential sustainability, since most of the outputs had only been completed immediately prior to the evaluation.

## Slide 8: Key recommendations of the evaluation
To Project managers and DA Coordination Division: Improve project management tools using internationally recognized best practices. Examples include the use of logical frameworks, consistent application of result-based financial budgeting and reporting, include a brief assessment against key evaluation criteria into the self-evaluation reports (rather than only conducting an intermediate assessment of results).
To WIPO Senior Management: Establish a system to collect data on who uses existing services as a basis to provide tailored information to specific target groups and to actively collect feed-back from them for the purpose of continuous improvement of its services.

## Slide 9: Key recommendations of the evaluation
To the WIPO Global Infrastructure Sector on formalizing coordination with other Sectors: Defining specific responsibilities to be assumed by each programme and requiring a formal sign-off by the programmes involved would help to ensure that coordination is less dependent on informal cooperation.
Notes: Coordination seems to depend much on personal relationships - which is a risk for projects, because staff and managers might change. In this particular case, coordination worked well.

## Slide 10: What worked well? Experience as a WIPO Evaluation Consultant
This was my first assignment for WIPO. As a „newcomer“ to WIPO, I appreciated first of all the support received in familiarizing myself with the organization.
No attempt of IAOD or the Project to push for desired evaluation results or “down-tune” critical comments in the report.
After some “warming up” during the briefing, all discussions with stakeholders were open and constructive. Persons interviewed openly shared information and freely exchanged views.
WIPO staff members supported the evaluation process actively (in particular also through arranging meetings with the right persons) and provided access to all relevant information.
Notes: No attempt by WIPO to „censure“ findings or conclusions or to prevent me from making recommendations.
Great support in arranging interviews and meeting schedules - very important. People are more and more reluctant to spend time for meeting evaluators.
Recent example of an ex-post evaluation for UNIDO, where interview partners/respondents to surveys were not able to clearly remember to what activities the surveys referred to

## Slide 11: What worked well? Experience as a WIPO Evaluation Consultant
The Project prepared well, e.g. actively conducted user surveys and made them available – crucial for evaluation!
The Project did use existing planning and monitoring tools and beyond minimum standards of WIPO even provided a result-based financial report (relating expenditures to outcomes and UN budget lines – this is best practice within the UN system).
Both IAOD and the project provided timely, detailed and meaningful feed-back on the report.
Notes: Recent example of an ex-post evaluation for UNIDO, where interview partners/respondents to surveys were not able to clearly remember to what activities the surveys referred to

## Slide 12: What could be improved?
Need to streamline ToRs. ToRs of 47 pages, partially with internal contradictions, especially with the Annexes. There is a risk that external evaluators with no prior evaluation experience will not understand the requirements of the job.
Need to consistently align ToRs with WIPO‘s evaluation policy. My ToRs did not for instance not require an assessment of efficiency („value for money“), which should be an essential question. Standard ToRs would make all evaluations comparable and useful as an input to other evaluations (e.g. Thematic Evaluations).
Need to clearly define the scope of work: All outputs required for an evaluation should be explicitly mentioned (including the meeting summaries). Otherwise, there is a risk that consultants will not deliver them, unless they are paid in addition.
Notes: Page 10 of ToRs: The expert will conduct semi-structured interviews based on an agreed protocol / list of questions.

## Slide 13: Conclusions
Project-cycle management tools (project planning, financial and operational reports) are not only important for monitoring, but also key inputs to evaluations. Further improvement is still possible.
Data collection of projects is crucial as a factual basis for evaluations, because data collected ex post is often not reliable. WIPO should in general retrieve more information about who uses which services and for what purpose.
A well formulated plan for the evaluation is crucial. WIPO rightly required a detailed inception report. There is room for enhancing consistency, clarity and completeness of evaluation ToRs.
Using a single approach and format (WIPO evaluation norms) for all evaluations would make them comparable and useful for larger evaluations (e.g. thematic evaluations).

## Slide 14: Conclusions
An evaluation should be a constructive, participatory process geared towards organizational learning (promoting self-learning), while still ensuring the accountability purpose of the evaluation. This requires a relationship of trust with no hidden agendas or politically motivated interference.
Whenever possible, evaluators should seek alignment on key evaluation results, because otherwise, recommendations are unlikely to be understood and implemented. For this purpose, a well prepared physical de-briefing is essential, if possible after comments on a draft report have been received.

## Slide 15: Conclusions
To summarize, working with WIPO has been an extremely positive, pleasant and enriching experience.
An understanding of everyone in WIPO what evaluation is pivotal. Let me therefore warmly congratulate WIPO for organising this important seminar. Let me also thank the IAOD for the kind invitation to contribute as a speaker. I hope you found this brief presentation useful and am happy to answer any questions you might have.
Thank you for your interest and attention!
Daniel Keller, Director, Swiss Consulting Co. Ltd. Hanoi, Vietnam
Management and Development Consultants
www.swissconsulting.com.vn